## Sheet1
Initiative_ID,Initiative_Name,Product_Line,Status,Start_Date,Target_Completion_Date,Actual_Completion_Date,Team_Size,Budget_Allocated,Budget_Spent,Resource_Utilization,Priority,Expected_Revenue_Impact,Actual_Revenue_Impact,Progress_Percentage,Assigned_Team
INIT0001,Analytics Suite - Feature 1,Analytics Suite,Testing,2023-02-14,2023-06-23,,8,1000000,617883,77,Medium,5000000,,80,Team Alpha
INIT0002,Mobile App - Feature 2,Mobile App,On Hold,2023-08-01,2023-10-08,,12,100000,75327,66,Low,100000,,25,Team Alpha
INIT0003,Analytics Suite - Feature 3,Analytics Suite,Planning,2023-06-26,2023-11-08,,10,250000,151608,96,Medium,5000000,,10,Team Epsilon
INIT0004,Mobile App - Feature 4,Mobile App,In Development,2023-03-15,2023-07-25,,8,50000,30831,75,Medium,100000,,50,Team Delta
INIT0005,Data Infrastructure - Feature 5,Data Infrastructure,Testing,2023-06-22,2023-10-07,,10,250000,131069,66,Medium,500000,,80,Team Alpha
INIT0006,Web Platform - Feature 6,Web Platform,Testing,2023-05-18,2023-10-01,,6,1000000,816443,88,Low,500000,,80,Team Gamma
INIT0007,Data Infrastructure - Feature 7,Data Infrastructure,Launched,2023-09-21,2023-11-30,2023-12-03,11,500000,204259,96,Medium,100000,62161,100,Team Alpha
INIT0008,Web Platform - Feature 8,Web Platform,Planning,2023-08-22,2023-10-03,,7,250000,215926,83,High,5000000,,10,Team Alpha
INIT0009,Analytics Suite - Feature 9,Analytics Suite,Launched,2023-05-04,2023-09-06,2023-09-08,10,100000,106841,97,Critical,1000000,740974,100,Team Alpha
INIT0010,API - Feature 10,API,Planning,2023-07-17,2023-08-28,,15,100000,98305,73,Medium,500000,,10,Team Alpha
INIT0011,Web Platform - Feature 11,Web Platform,In Development,2023-09-20,2023-10-25,,5,50000,33963,71,Medium,100000,,50,Team Delta
INIT0012,Web Platform - Feature 12,Web Platform,Testing,2023-08-05,2023-12-09,,6,250000,166799,89,Medium,1000000,,80,Team Gamma
INIT0013,Analytics Suite - Feature 13,Analytics Suite,On Hold,2023-02-22,2023-03-25,,8,1000000,1099543,95,Low,1000000,,25,Team Epsilon
INIT0014,API - Feature 14,API,Planning,2023-06-22,2023-09-30,,7,250000,247298,79,Low,500000,,10,Team Alpha
INIT0015,Web Platform - Feature 15,Web Platform,On Hold,2023-11-04,2024-03-16,,14,250000,211151,61,High,5000000,,25,Team Alpha
INIT0016,API - Feature 16,API,Testing,2023-07-18,2023-08-26,,12,1000000,866455,72,Low,1000000,,80,Team Delta
INIT0017,Web Platform - Feature 17,Web Platform,On Hold,2023-09-17,2024-01-01,,11,100000,97251,71,Low,1000000,,25,Team Gamma
INIT0018,Mobile App - Feature 18,Mobile App,Launched,2023-10-14,2023-12-29,2024-01-24,6,50000,23890,79,High,5000000,5258316,100,Team Gamma
INIT0019,API - Feature 19,API,Testing,2023-05-31,2023-10-26,,13,50000,33821,97,Medium,100000,,80,Team Epsilon
INIT0020,Data Infrastructure - Feature 20,Data Infrastructure,In Development,2023-09-29,2024-01-13,,5,500000,171624,68,Critical,500000,,50,Team Delta
INIT0021,API - Feature 21,API,Launched,2023-06-11,2023-08-26,2023-10-01,5,250000,201206,80,Low,100000,50329,100,Team Beta
INIT0022,API - Feature 22,API,In Development,2023-03-23,2023-08-25,,9,50000,20176,100,High,5000000,,50,Team Epsilon
INIT0023,Data Infrastructure - Feature 23,Data Infrastructure,Launched,2023-01-03,2023-02-11,2023-02-11,15,50000,50680,93,Low,500000,256270,100,Team Delta
INIT0024,Mobile App - Feature 24,Mobile App,In Development,2023-06-09,2023-08-11,,12,50000,30342,79,High,500000,,50,Team Gamma
INIT0025,Mobile App - Feature 25,Mobile App,Planning,2023-08-22,2024-02-01,,9,1000000,719294,68,Medium,1000000,,10,Team Gamma
INIT0026,Data Infrastructure - Feature 26,Data Infrastructure,Testing,2023-07-26,2023-08-29,,5,100000,47945,73,High,100000,,80,Team Beta
INIT0027,Analytics Suite - Feature 27,Analytics Suite,On Hold,2023-07-07,2023-08-15,,7,500000,500617,94,High,100000,,25,Team Alpha
INIT0028,Analytics Suite - Feature 28,Analytics Suite,Planning,2023-01-25,2023-03-25,,4,500000,327725,95,Critical,1000000,,10,Team Alpha
INIT0029,Data Infrastructure - Feature 29,Data Infrastructure,In Development,2023-06-04,2023-10-19,,7,50000,41499,99,High,500000,,50,Team Alpha
INIT0030,Data Infrastructure - Feature 30,Data Infrastructure,Planning,2023-02-28,2023-04-26,,6,500000,229458,76,Critical,500000,,10,Team Gamma
INIT0031,API - Feature 31,API,Launched,2023-01-21,2023-07-10,2023-07-08,3,500000,282241,60,Medium,100000,113481,100,Team Beta
INIT0032,Analytics Suite - Feature 32,Analytics Suite,Launched,2023-09-19,2023-11-07,2023-11-18,10,250000,203867,78,High,1000000,824994,100,Team Alpha
INIT0033,Mobile App - Feature 33,Mobile App,In Development,2023-07-04,2023-10-22,,4,500000,445416,62,Critical,100000,,50,Team Gamma
INIT0034,Web Platform - Feature 34,Web Platform,In Development,2023-08-13,2023-11-19,,8,50000,29904,71,Medium,100000,,50,Team Gamma
INIT0035,Data Infrastructure - Feature 35,Data Infrastructure,Launched,2023-07-17,2023-12-16,2024-01-31,14,100000,39044,63,Low,500000,286299,100,Team Gamma
INIT0036,Analytics Suite - Feature 36,Analytics Suite,Launched,2023-11-09,2024-03-15,2024-04-28,14,50000,49503,68,Low,5000000,5721392,100,Team Beta
INIT0037,Mobile App - Feature 37,Mobile App,Launched,2023-02-02,2023-05-09,2023-05-04,12,1000000,914022,96,Low,500000,592263,100,Team Alpha
INIT0038,API - Feature 38,API,On Hold,2023-12-05,2024-03-07,,13,500000,288299,84,Critical,500000,,25,Team Delta
INIT0039,Analytics Suite - Feature 39,Analytics Suite,On Hold,2023-11-26,2024-02-04,,10,1000000,979076,70,Critical,100000,,25,Team Alpha
INIT0040,Data Infrastructure - Feature 40,Data Infrastructure,Testing,2023-05-23,2023-07-04,,13,1000000,478165,84,High,5000000,,80,Team Gamma
INIT0041,Web Platform - Feature 41,Web Platform,Planning,2023-10-21,2024-03-13,,10,50000,49263,80,Low,100000,,10,Team Delta
INIT0042,Data Infrastructure - Feature 42,Data Infrastructure,Planning,2023-07-31,2023-09-08,,4,1000000,739279,98,Critical,1000000,,10,Team Delta
INIT0043,Analytics Suite - Feature 43,Analytics Suite,On Hold,2023-06-24,2023-10-25,,10,50000,47663,81,High,5000000,,25,Team Delta
INIT0044,API - Feature 44,API,Launched,2023-12-04,2024-02-28,2024-02-28,8,250000,184538,66,Critical,100000,112781,100,Team Alpha
INIT0045,Data Infrastructure - Feature 45,Data Infrastructure,In Development,2023-05-11,2023-07-30,,9,100000,39659,73,Low,5000000,,50,Team Alpha
INIT0046,Web Platform - Feature 46,Web Platform,Testing,2023-01-24,2023-07-23,,10,50000,45885,89,Critical,500000,,80,Team Delta
INIT0047,Data Infrastructure - Feature 47,Data Infrastructure,Planning,2023-08-10,2024-02-05,,15,500000,519748,71,Critical,500000,,10,Team Epsilon
INIT0048,Web Platform - Feature 48,Web Platform,Planning,2023-11-07,2024-02-27,,9,1000000,1005112,98,Low,500000,,10,Team Epsilon
INIT0049,API - Feature 49,API,Launched,2023-08-20,2023-10-23,2023-10-27,14,1000000,539130,95,Medium,1000000,998312,100,Team Gamma
INIT0050,Analytics Suite - Feature 50,Analytics Suite,In Development,2023-11-16,2024-02-28,,5,250000,259238,71,High,1000000,,50,Team Beta
INIT0051,Mobile App - Feature 51,Mobile App,Testing,2023-10-20,2024-03-04,,9,1000000,528742,60,Low,100000,,80,Team Epsilon
INIT0052,Mobile App - Feature 52,Mobile App,Launched,2023-12-10,2024-01-23,2024-01-20,5,250000,211678,63,High,1000000,642800,100,Team Alpha
INIT0053,Analytics Suite - Feature 53,Analytics Suite,Planning,2023-02-22,2023-08-14,,11,100000,89393,84,Medium,500000,,10,Team Delta
INIT0054,Analytics Suite - Feature 54,Analytics Suite,Testing,2023-07-18,2023-12-01,,3,250000,268166,60,Critical,1000000,,80,Team Delta
INIT0055,Web Platform - Feature 55,Web Platform,On Hold,2023-11-21,2024-03-24,,12,1000000,737292,72,Low,500000,,25,Team Beta
INIT0056,API - Feature 56,API,Launched,2023-04-06,2023-06-19,2023-07-01,7,500000,166253,95,High,1000000,591046,100,Team Alpha
INIT0057,Analytics Suite - Feature 57,Analytics Suite,Testing,2023-08-27,2023-11-04,,8,50000,21148,98,Critical,100000,,80,Team Gamma
INIT0058,Analytics Suite - Feature 58,Analytics Suite,Testing,2023-10-09,2024-02-07,,8,50000,46361,93,Low,500000,,80,Team Epsilon
INIT0059,Web Platform - Feature 59,Web Platform,On Hold,2023-03-23,2023-08-06,,4,1000000,729628,82,Critical,500000,,25,Team Epsilon
INIT0060,Web Platform - Feature 60,Web Platform,Testing,2023-05-31,2023-08-24,,11,1000000,724399,60,Medium,100000,,80,Team Gamma
INIT0061,API - Feature 61,API,Launched,2023-11-15,2024-02-15,2024-04-03,15,250000,151274,67,High,5000000,3398066,100,Team Epsilon
INIT0062,API - Feature 62,API,Planning,2023-09-18,2024-02-09,,13,500000,167540,72,Medium,1000000,,10,Team Epsilon
INIT0063,Analytics Suite - Feature 63,Analytics Suite,Planning,2023-10-03,2024-03-17,,6,50000,40077,100,Critical,500000,,10,Team Beta
INIT0064,Data Infrastructure - Feature 64,Data Infrastructure,Planning,2023-12-26,2024-05-15,,5,50000,44875,61,High,5000000,,10,Team Epsilon
INIT0065,API - Feature 65,API,Planning,2023-01-28,2023-04-13,,12,250000,186616,74,Critical,1000000,,10,Team Alpha
INIT0066,Data Infrastructure - Feature 66,Data Infrastructure,Launched,2023-08-10,2023-11-28,2023-12-03,13,50000,36393,99,Low,100000,102917,100,Team Delta
INIT0067,Analytics Suite - Feature 67,Analytics Suite,Planning,2023-09-15,2023-11-11,,7,250000,232378,98,Critical,100000,,10,Team Gamma
INIT0068,API - Feature 68,API,Launched,2023-12-05,2024-01-11,2024-01-14,9,100000,40910,94,Low,1000000,1172093,100,Team Delta
INIT0069,Web Platform - Feature 69,Web Platform,Testing,2023-10-11,2024-03-31,,3,100000,39858,96,Medium,5000000,,80,Team Alpha
INIT0070,Analytics Suite - Feature 70,Analytics Suite,On Hold,2023-04-18,2023-08-14,,13,100000,63012,92,Critical,500000,,25,Team Gamma
INIT0071,Web Platform - Feature 71,Web Platform,In Development,2023-05-10,2023-07-28,,15,50000,22254,96,High,100000,,50,Team Epsilon
INIT0072,Analytics Suite - Feature 72,Analytics Suite,Launched,2023-12-10,2024-01-26,2024-01-24,8,1000000,689752,82,Critical,500000,484953,100,Team Gamma
INIT0073,Web Platform - Feature 73,Web Platform,Planning,2023-02-05,2023-04-25,,8,250000,172172,99,Medium,1000000,,10,Team Epsilon
INIT0074,Analytics Suite - Feature 74,Analytics Suite,In Development,2023-08-08,2023-10-20,,15,50000,27528,74,Medium,5000000,,50,Team Gamma
INIT0075,API - Feature 75,API,Testing,2023-09-03,2024-01-29,,7,500000,293496,91,High,100000,,80,Team Gamma
INIT0076,Web Platform - Feature 76,Web Platform,On Hold,2023-03-13,2023-08-27,,13,100000,51058,64,Critical,100000,,25,Team Gamma
INIT0077,Mobile App - Feature 77,Mobile App,On Hold,2023-10-24,2024-03-05,,3,1000000,470208,95,Critical,1000000,,25,Team Epsilon
INIT0078,Analytics Suite - Feature 78,Analytics Suite,On Hold,2023-07-07,2023-11-14,,12,100000,101315,78,Low,500000,,25,Team Beta
INIT0079,Data Infrastructure - Feature 79,Data Infrastructure,On Hold,2023-07-06,2023-12-11,,15,50000,41507,99,Critical,500000,,25,Team Delta
INIT0080,Analytics Suite - Feature 80,Analytics Suite,In Development,2023-04-02,2023-09-23,,5,1000000,827530,90,Low,1000000,,50,Team Beta