## Raw_Data
Initiative_ID | Initiative_Name | Product_Line | Status | Start_Date | Target_Completion_Date | Actual_Completion_Date | Team_Size | Budget_Allocated | Budget_Spent | Resource_Utilization | Priority | Expected_Revenue_Impact | Actual_Revenue_Impact | Progress_Percentage | Assigned_Team | Planned_Duration | Actual_Duration | Schedule_Variance_Days | OnTime | Budget_Variance_Amount | Budget_Variance_Pct | BudgetVarBin | ScheduleVarBin | Start_Offset
INIT0001 | Analytics Suite - Feature 1 | Analytics Suite | Testing | 2023-02-14 | 2023-06-23 |  | 8 | 1000000 | 617883 | 77 | Medium | 5000000 |  | 80 | Team Alpha | 129 |  | 860 | 0 | 382117 | -0.38212 | (-inf, -0.2] | (30.0, inf] | 42
INIT0002 | Mobile App - Feature 2 | Mobile App | On Hold | 2023-08-01 | 2023-10-08 |  | 12 | 100000 | 75327 | 66 | Low | 100000 |  | 25 | Team Alpha | 68 |  | 753 | 0 | 24673 | -0.24673 | (-inf, -0.2] | (30.0, inf] | 210
INIT0003 | Analytics Suite - Feature 3 | Analytics Suite | Planning | 2023-06-26 | 2023-11-08 |  | 10 | 250000 | 151608 | 96 | Medium | 5000000 |  | 10 | Team Epsilon | 135 |  | 722 | 0 | 98392 | -0.39357 | (-inf, -0.2] | (30.0, inf] | 174
INIT0004 | Mobile App - Feature 4 | Mobile App | In Development | 2023-03-15 | 2023-07-25 |  | 8 | 50000 | 30831 | 75 | Medium | 100000 |  | 50 | Team Delta | 132 |  | 828 | 0 | 19169 | -0.38338 | (-inf, -0.2] | (30.0, inf] | 71
INIT0005 | Data Infrastructure - Feature 5 | Data Infrastructure | Testing | 2023-06-22 | 2023-10-07 |  | 10 | 250000 | 131069 | 66 | Medium | 500000 |  | 80 | Team Alpha | 107 |  | 754 | 0 | 118931 | -0.47572 | (-inf, -0.2] | (30.0, inf] | 170
INIT0006 | Web Platform - Feature 6 | Web Platform | Testing | 2023-05-18 | 2023-10-01 |  | 6 | 1000000 | 816443 | 88 | Low | 500000 |  | 80 | Team Gamma | 136 |  | 760 | 0 | 183557 | -0.18356 | (-0.2, -0.1] | (30.0, inf] | 135
INIT0007 | Data Infrastructure - Feature 7 | Data Infrastructure | Launched | 2023-09-21 | 2023-11-30 | 2023-12-03 | 11 | 500000 | 204259 | 96 | Medium | 100000 | 62161 | 100 | Team Alpha | 70 | 73 | 3 | 0 | 295741 | -0.59148 | (-inf, -0.2] | (0.0, 10.0] | 261
INIT0008 | Web Platform - Feature 8 | Web Platform | Planning | 2023-08-22 | 2023-10-03 |  | 7 | 250000 | 215926 | 83 | High | 5000000 |  | 10 | Team Alpha | 42 |  | 758 | 0 | 34074 | -0.1363 | (-0.2, -0.1] | (30.0, inf] | 231
INIT0009 | Analytics Suite - Feature 9 | Analytics Suite | Launched | 2023-05-04 | 2023-09-06 | 2023-09-08 | 10 | 100000 | 106841 | 97 | Critical | 1000000 | 740974 | 100 | Team Alpha | 125 | 127 | 2 | 0 | -6841 | 0.06841 | (0.0, 0.1] | (0.0, 10.0] | 121
INIT0010 | API - Feature 10 | API | Planning | 2023-07-17 | 2023-08-28 |  | 15 | 100000 | 98305 | 73 | Medium | 500000 |  | 10 | Team Alpha | 42 |  | 794 | 0 | 1695 | -0.01695 | (-0.1, 0.0] | (30.0, inf] | 195
INIT0011 | Web Platform - Feature 11 | Web Platform | In Development | 2023-09-20 | 2023-10-25 |  | 5 | 50000 | 33963 | 71 | Medium | 100000 |  | 50 | Team Delta | 35 |  | 736 | 0 | 16037 | -0.32074 | (-inf, -0.2] | (30.0, inf] | 260
INIT0012 | Web Platform - Feature 12 | Web Platform | Testing | 2023-08-05 | 2023-12-09 |  | 6 | 250000 | 166799 | 89 | Medium | 1000000 |  | 80 | Team Gamma | 126 |  | 691 | 0 | 83201 | -0.3328 | (-inf, -0.2] | (30.0, inf] | 214
INIT0013 | Analytics Suite - Feature 13 | Analytics Suite | On Hold | 2023-02-22 | 2023-03-25 |  | 8 | 1000000 | 1099543 | 95 | Low | 1000000 |  | 25 | Team Epsilon | 31 |  | 950 | 0 | -99543 | 0.099543 | (0.0, 0.1] | (30.0, inf] | 50
INIT0014 | API - Feature 14 | API | Planning | 2023-06-22 | 2023-09-30 |  | 7 | 250000 | 247298 | 79 | Low | 500000 |  | 10 | Team Alpha | 100 |  | 761 | 0 | 2702 | -0.010808 | (-0.1, 0.0] | (30.0, inf] | 170
INIT0015 | Web Platform - Feature 15 | Web Platform | On Hold | 2023-11-04 | 2024-03-16 |  | 14 | 250000 | 211151 | 61 | High | 5000000 |  | 25 | Team Alpha | 133 |  | 593 | 0 | 38849 | -0.1554 | (-0.2, -0.1] | (30.0, inf] | 305
INIT0016 | API - Feature 16 | API | Testing | 2023-07-18 | 2023-08-26 |  | 12 | 1000000 | 866455 | 72 | Low | 1000000 |  | 80 | Team Delta | 39 |  | 796 | 0 | 133545 | -0.13354 | (-0.2, -0.1] | (30.0, inf] | 196
INIT0017 | Web Platform - Feature 17 | Web Platform | On Hold | 2023-09-17 | 2024-01-01 |  | 11 | 100000 | 97251 | 71 | Low | 1000000 |  | 25 | Team Gamma | 106 |  | 668 | 0 | 2749 | -0.02749 | (-0.1, 0.0] | (30.0, inf] | 257
INIT0018 | Mobile App - Feature 18 | Mobile App | Launched | 2023-10-14 | 2023-12-29 | 2024-01-24 | 6 | 50000 | 23890 | 79 | High | 5000000 | 5258316 | 100 | Team Gamma | 76 | 102 | 26 | 0 | 26110 | -0.5222 | (-inf, -0.2] | (10.0, 30.0] | 284
INIT0019 | API - Feature 19 | API | Testing | 2023-05-31 | 2023-10-26 |  | 13 | 50000 | 33821 | 97 | Medium | 100000 |  | 80 | Team Epsilon | 148 |  | 735 | 0 | 16179 | -0.32358 | (-inf, -0.2] | (30.0, inf] | 148
INIT0020 | Data Infrastructure - Feature 20 | Data Infrastructure | In Development | 2023-09-29 | 2024-01-13 |  | 5 | 500000 | 171624 | 68 | Critical | 500000 |  | 50 | Team Delta | 106 |  | 656 | 0 | 328376 | -0.65675 | (-inf, -0.2] | (30.0, inf] | 269
INIT0021 | API - Feature 21 | API | Launched | 2023-06-11 | 2023-08-26 | 2023-10-01 | 5 | 250000 | 201206 | 80 | Low | 100000 | 50329 | 100 | Team Beta | 76 | 112 | 36 | 0 | 48794 | -0.19518 | (-0.2, -0.1] | (30.0, inf] | 159
INIT0022 | API - Feature 22 | API | In Development | 2023-03-23 | 2023-08-25 |  | 9 | 50000 | 20176 | 100 | High | 5000000 |  | 50 | Team Epsilon | 155 |  | 797 | 0 | 29824 | -0.59648 | (-inf, -0.2] | (30.0, inf] | 79
INIT0023 | Data Infrastructure - Feature 23 | Data Infrastructure | Launched | 2023-01-03 | 2023-02-11 | 2023-02-11 | 15 | 50000 | 50680 | 93 | Low | 500000 | 256270 | 100 | Team Delta | 39 | 39 | 0 | 1 | -680 | 0.0136 | (0.0, 0.1] | (-10.0, 0.0] | 0
INIT0024 | Mobile App - Feature 24 | Mobile App | In Development | 2023-06-09 | 2023-08-11 |  | 12 | 50000 | 30342 | 79 | High | 500000 |  | 50 | Team Gamma | 63 |  | 811 | 0 | 19658 | -0.39316 | (-inf, -0.2] | (30.0, inf] | 157
INIT0025 | Mobile App - Feature 25 | Mobile App | Planning | 2023-08-22 | 2024-02-01 |  | 9 | 1000000 | 719294 | 68 | Medium | 1000000 |  | 10 | Team Gamma | 163 |  | 637 | 0 | 280706 | -0.28071 | (-inf, -0.2] | (30.0, inf] | 231
INIT0026 | Data Infrastructure - Feature 26 | Data Infrastructure | Testing | 2023-07-26 | 2023-08-29 |  | 5 | 100000 | 47945 | 73 | High | 100000 |  | 80 | Team Beta | 34 |  | 793 | 0 | 52055 | -0.52055 | (-inf, -0.2] | (30.0, inf] | 204
INIT0027 | Analytics Suite - Feature 27 | Analytics Suite | On Hold | 2023-07-07 | 2023-08-15 |  | 7 | 500000 | 500617 | 94 | High | 100000 |  | 25 | Team Alpha | 39 |  | 807 | 0 | -617 | 0.001234 | (0.0, 0.1] | (30.0, inf] | 185
INIT0028 | Analytics Suite - Feature 28 | Analytics Suite | Planning | 2023-01-25 | 2023-03-25 |  | 4 | 500000 | 327725 | 95 | Critical | 1000000 |  | 10 | Team Alpha | 59 |  | 950 | 0 | 172275 | -0.34455 | (-inf, -0.2] | (30.0, inf] | 22
INIT0029 | Data Infrastructure - Feature 29 | Data Infrastructure | In Development | 2023-06-04 | 2023-10-19 |  | 7 | 50000 | 41499 | 99 | High | 500000 |  | 50 | Team Alpha | 137 |  | 742 | 0 | 8501 | -0.17002 | (-0.2, -0.1] | (30.0, inf] | 152
INIT0030 | Data Infrastructure - Feature 30 | Data Infrastructure | Planning | 2023-02-28 | 2023-04-26 |  | 6 | 500000 | 229458 | 76 | Critical | 500000 |  | 10 | Team Gamma | 57 |  | 918 | 0 | 270542 | -0.54108 | (-inf, -0.2] | (30.0, inf] | 56
INIT0031 | API - Feature 31 | API | Launched | 2023-01-21 | 2023-07-10 | 2023-07-08 | 3 | 500000 | 282241 | 60 | Medium | 100000 | 113481 | 100 | Team Beta | 170 | 168 | -2 | 1 | 217759 | -0.43552 | (-inf, -0.2] | (-10.0, 0.0] | 18
INIT0032 | Analytics Suite - Feature 32 | Analytics Suite | Launched | 2023-09-19 | 2023-11-07 | 2023-11-18 | 10 | 250000 | 203867 | 78 | High | 1000000 | 824994 | 100 | Team Alpha | 49 | 60 | 11 | 0 | 46133 | -0.18453 | (-0.2, -0.1] | (10.0, 30.0] | 259
INIT0033 | Mobile App - Feature 33 | Mobile App | In Development | 2023-07-04 | 2023-10-22 |  | 4 | 500000 | 445416 | 62 | Critical | 100000 |  | 50 | Team Gamma | 110 |  | 739 | 0 | 54584 | -0.10917 | (-0.2, -0.1] | (30.0, inf] | 182
INIT0034 | Web Platform - Feature 34 | Web Platform | In Development | 2023-08-13 | 2023-11-19 |  | 8 | 50000 | 29904 | 71 | Medium | 100000 |  | 50 | Team Gamma | 98 |  | 711 | 0 | 20096 | -0.40192 | (-inf, -0.2] | (30.0, inf] | 222
INIT0035 | Data Infrastructure - Feature 35 | Data Infrastructure | Launched | 2023-07-17 | 2023-12-16 | 2024-01-31 | 14 | 100000 | 39044 | 63 | Low | 500000 | 286299 | 100 | Team Gamma | 152 | 198 | 46 | 0 | 60956 | -0.60956 | (-inf, -0.2] | (30.0, inf] | 195
INIT0036 | Analytics Suite - Feature 36 | Analytics Suite | Launched | 2023-11-09 | 2024-03-15 | 2024-04-28 | 14 | 50000 | 49503 | 68 | Low | 5000000 | 5721392 | 100 | Team Beta | 127 | 171 | 44 | 0 | 497 | -0.00994 | (-0.1, 0.0] | (30.0, inf] | 310
INIT0037 | Mobile App - Feature 37 | Mobile App | Launched | 2023-02-02 | 2023-05-09 | 2023-05-04 | 12 | 1000000 | 914022 | 96 | Low | 500000 | 592263 | 100 | Team Alpha | 96 | 91 | -5 | 1 | 85978 | -0.085978 | (-0.1, 0.0] | (-10.0, 0.0] | 30
INIT0038 | API - Feature 38 | API | On Hold | 2023-12-05 | 2024-03-07 |  | 13 | 500000 | 288299 | 84 | Critical | 500000 |  | 25 | Team Delta | 93 |  | 602 | 0 | 211701 | -0.4234 | (-inf, -0.2] | (30.0, inf] | 336
INIT0039 | Analytics Suite - Feature 39 | Analytics Suite | On Hold | 2023-11-26 | 2024-02-04 |  | 10 | 1000000 | 979076 | 70 | Critical | 100000 |  | 25 | Team Alpha | 70 |  | 634 | 0 | 20924 | -0.020924 | (-0.1, 0.0] | (30.0, inf] | 327
INIT0040 | Data Infrastructure - Feature 40 | Data Infrastructure | Testing | 2023-05-23 | 2023-07-04 |  | 13 | 1000000 | 478165 | 84 | High | 5000000 |  | 80 | Team Gamma | 42 |  | 849 | 0 | 521835 | -0.52184 | (-inf, -0.2] | (30.0, inf] | 140
INIT0041 | Web Platform - Feature 41 | Web Platform | Planning | 2023-10-21 | 2024-03-13 |  | 10 | 50000 | 49263 | 80 | Low | 100000 |  | 10 | Team Delta | 144 |  | 596 | 0 | 737 | -0.01474 | (-0.1, 0.0] | (30.0, inf] | 291
INIT0042 | Data Infrastructure - Feature 42 | Data Infrastructure | Planning | 2023-07-31 | 2023-09-08 |  | 4 | 1000000 | 739279 | 98 | Critical | 1000000 |  | 10 | Team Delta | 39 |  | 783 | 0 | 260721 | -0.26072 | (-inf, -0.2] | (30.0, inf] | 209
INIT0043 | Analytics Suite - Feature 43 | Analytics Suite | On Hold | 2023-06-24 | 2023-10-25 |  | 10 | 50000 | 47663 | 81 | High | 5000000 |  | 25 | Team Delta | 123 |  | 736 | 0 | 2337 | -0.04674 | (-0.1, 0.0] | (30.0, inf] | 172
INIT0044 | API - Feature 44 | API | Launched | 2023-12-04 | 2024-02-28 | 2024-02-28 | 8 | 250000 | 184538 | 66 | Critical | 100000 | 112781 | 100 | Team Alpha | 86 | 86 | 0 | 1 | 65462 | -0.26185 | (-inf, -0.2] | (-10.0, 0.0] | 335
INIT0045 | Data Infrastructure - Feature 45 | Data Infrastructure | In Development | 2023-05-11 | 2023-07-30 |  | 9 | 100000 | 39659 | 73 | Low | 5000000 |  | 50 | Team Alpha | 80 |  | 823 | 0 | 60341 | -0.60341 | (-inf, -0.2] | (30.0, inf] | 128
INIT0046 | Web Platform - Feature 46 | Web Platform | Testing | 2023-01-24 | 2023-07-23 |  | 10 | 50000 | 45885 | 89 | Critical | 500000 |  | 80 | Team Delta | 180 |  | 830 | 0 | 4115 | -0.0823 | (-0.1, 0.0] | (30.0, inf] | 21
INIT0047 | Data Infrastructure - Feature 47 | Data Infrastructure | Planning | 2023-08-10 | 2024-02-05 |  | 15 | 500000 | 519748 | 71 | Critical | 500000 |  | 10 | Team Epsilon | 179 |  | 633 | 0 | -19748 | 0.039496 | (0.0, 0.1] | (30.0, inf] | 219
INIT0048 | Web Platform - Feature 48 | Web Platform | Planning | 2023-11-07 | 2024-02-27 |  | 9 | 1000000 | 1005112 | 98 | Low | 500000 |  | 10 | Team Epsilon | 112 |  | 611 | 0 | -5112 | 0.005112 | (0.0, 0.1] | (30.0, inf] | 308
INIT0049 | API - Feature 49 | API | Launched | 2023-08-20 | 2023-10-23 | 2023-10-27 | 14 | 1000000 | 539130 | 95 | Medium | 1000000 | 998312 | 100 | Team Gamma | 64 | 68 | 4 | 0 | 460870 | -0.46087 | (-inf, -0.2] | (0.0, 10.0] | 229
INIT0050 | Analytics Suite - Feature 50 | Analytics Suite | In Development | 2023-11-16 | 2024-02-28 |  | 5 | 250000 | 259238 | 71 | High | 1000000 |  | 50 | Team Beta | 104 |  | 610 | 0 | -9238 | 0.036952 | (0.0, 0.1] | (30.0, inf] | 317
INIT0051 | Mobile App - Feature 51 | Mobile App | Testing | 2023-10-20 | 2024-03-04 |  | 9 | 1000000 | 528742 | 60 | Low | 100000 |  | 80 | Team Epsilon | 136 |  | 605 | 0 | 471258 | -0.47126 | (-inf, -0.2] | (30.0, inf] | 290
INIT0052 | Mobile App - Feature 52 | Mobile App | Launched | 2023-12-10 | 2024-01-23 | 2024-01-20 | 5 | 250000 | 211678 | 63 | High | 1000000 | 642800 | 100 | Team Alpha | 44 | 41 | -3 | 1 | 38322 | -0.15329 | (-0.2, -0.1] | (-10.0, 0.0] | 341
INIT0053 | Analytics Suite - Feature 53 | Analytics Suite | Planning | 2023-02-22 | 2023-08-14 |  | 11 | 100000 | 89393 | 84 | Medium | 500000 |  | 10 | Team Delta | 173 |  | 808 | 0 | 10607 | -0.10607 | (-0.2, -0.1] | (30.0, inf] | 50
INIT0054 | Analytics Suite - Feature 54 | Analytics Suite | Testing | 2023-07-18 | 2023-12-01 |  | 3 | 250000 | 268166 | 60 | Critical | 1000000 |  | 80 | Team Delta | 136 |  | 699 | 0 | -18166 | 0.072664 | (0.0, 0.1] | (30.0, inf] | 196
INIT0055 | Web Platform - Feature 55 | Web Platform | On Hold | 2023-11-21 | 2024-03-24 |  | 12 | 1000000 | 737292 | 72 | Low | 500000 |  | 25 | Team Beta | 124 |  | 585 | 0 | 262708 | -0.26271 | (-inf, -0.2] | (30.0, inf] | 322
INIT0056 | API - Feature 56 | API | Launched | 2023-04-06 | 2023-06-19 | 2023-07-01 | 7 | 500000 | 166253 | 95 | High | 1000000 | 591046 | 100 | Team Alpha | 74 | 86 | 12 | 0 | 333747 | -0.66749 | (-inf, -0.2] | (10.0, 30.0] | 93
INIT0057 | Analytics Suite - Feature 57 | Analytics Suite | Testing | 2023-08-27 | 2023-11-04 |  | 8 | 50000 | 21148 | 98 | Critical | 100000 |  | 80 | Team Gamma | 69 |  | 726 | 0 | 28852 | -0.57704 | (-inf, -0.2] | (30.0, inf] | 236
INIT0058 | Analytics Suite - Feature 58 | Analytics Suite | Testing | 2023-10-09 | 2024-02-07 |  | 8 | 50000 | 46361 | 93 | Low | 500000 |  | 80 | Team Epsilon | 121 |  | 631 | 0 | 3639 | -0.07278 | (-0.1, 0.0] | (30.0, inf] | 279
INIT0059 | Web Platform - Feature 59 | Web Platform | On Hold | 2023-03-23 | 2023-08-06 |  | 4 | 1000000 | 729628 | 82 | Critical | 500000 |  | 25 | Team Epsilon | 136 |  | 816 | 0 | 270372 | -0.27037 | (-inf, -0.2] | (30.0, inf] | 79
INIT0060 | Web Platform - Feature 60 | Web Platform | Testing | 2023-05-31 | 2023-08-24 |  | 11 | 1000000 | 724399 | 60 | Medium | 100000 |  | 80 | Team Gamma | 85 |  | 798 | 0 | 275601 | -0.2756 | (-inf, -0.2] | (30.0, inf] | 148
INIT0061 | API - Feature 61 | API | Launched | 2023-11-15 | 2024-02-15 | 2024-04-03 | 15 | 250000 | 151274 | 67 | High | 5000000 | 3398066 | 100 | Team Epsilon | 92 | 140 | 48 | 0 | 98726 | -0.3949 | (-inf, -0.2] | (30.0, inf] | 316
INIT0062 | API - Feature 62 | API | Planning | 2023-09-18 | 2024-02-09 |  | 13 | 500000 | 167540 | 72 | Medium | 1000000 |  | 10 | Team Epsilon | 144 |  | 629 | 0 | 332460 | -0.66492 | (-inf, -0.2] | (30.0, inf] | 258
INIT0063 | Analytics Suite - Feature 63 | Analytics Suite | Planning | 2023-10-03 | 2024-03-17 |  | 6 | 50000 | 40077 | 100 | Critical | 500000 |  | 10 | Team Beta | 166 |  | 592 | 0 | 9923 | -0.19846 | (-0.2, -0.1] | (30.0, inf] | 273
INIT0064 | Data Infrastructure - Feature 64 | Data Infrastructure | Planning | 2023-12-26 | 2024-05-15 |  | 5 | 50000 | 44875 | 61 | High | 5000000 |  | 10 | Team Epsilon | 141 |  | 533 | 0 | 5125 | -0.1025 | (-0.2, -0.1] | (30.0, inf] | 357
INIT0065 | API - Feature 65 | API | Planning | 2023-01-28 | 2023-04-13 |  | 12 | 250000 | 186616 | 74 | Critical | 1000000 |  | 10 | Team Alpha | 75 |  | 931 | 0 | 63384 | -0.25354 | (-inf, -0.2] | (30.0, inf] | 25
INIT0066 | Data Infrastructure - Feature 66 | Data Infrastructure | Launched | 2023-08-10 | 2023-11-28 | 2023-12-03 | 13 | 50000 | 36393 | 99 | Low | 100000 | 102917 | 100 | Team Delta | 110 | 115 | 5 | 0 | 13607 | -0.27214 | (-inf, -0.2] | (0.0, 10.0] | 219
INIT0067 | Analytics Suite - Feature 67 | Analytics Suite | Planning | 2023-09-15 | 2023-11-11 |  | 7 | 250000 | 232378 | 98 | Critical | 100000 |  | 10 | Team Gamma | 57 |  | 719 | 0 | 17622 | -0.070488 | (-0.1, 0.0] | (30.0, inf] | 255
INIT0068 | API - Feature 68 | API | Launched | 2023-12-05 | 2024-01-11 | 2024-01-14 | 9 | 100000 | 40910 | 94 | Low | 1000000 | 1172093 | 100 | Team Delta | 37 | 40 | 3 | 0 | 59090 | -0.5909 | (-inf, -0.2] | (0.0, 10.0] | 336
INIT0069 | Web Platform - Feature 69 | Web Platform | Testing | 2023-10-11 | 2024-03-31 |  | 3 | 100000 | 39858 | 96 | Medium | 5000000 |  | 80 | Team Alpha | 172 |  | 578 | 0 | 60142 | -0.60142 | (-inf, -0.2] | (30.0, inf] | 281
INIT0070 | Analytics Suite - Feature 70 | Analytics Suite | On Hold | 2023-04-18 | 2023-08-14 |  | 13 | 100000 | 63012 | 92 | Critical | 500000 |  | 25 | Team Gamma | 118 |  | 808 | 0 | 36988 | -0.36988 | (-inf, -0.2] | (30.0, inf] | 105
INIT0071 | Web Platform - Feature 71 | Web Platform | In Development | 2023-05-10 | 2023-07-28 |  | 15 | 50000 | 22254 | 96 | High | 100000 |  | 50 | Team Epsilon | 79 |  | 825 | 0 | 27746 | -0.55492 | (-inf, -0.2] | (30.0, inf] | 127
INIT0072 | Analytics Suite - Feature 72 | Analytics Suite | Launched | 2023-12-10 | 2024-01-26 | 2024-01-24 | 8 | 1000000 | 689752 | 82 | Critical | 500000 | 484953 | 100 | Team Gamma | 47 | 45 | -2 | 1 | 310248 | -0.31025 | (-inf, -0.2] | (-10.0, 0.0] | 341
INIT0073 | Web Platform - Feature 73 | Web Platform | Planning | 2023-02-05 | 2023-04-25 |  | 8 | 250000 | 172172 | 99 | Medium | 1000000 |  | 10 | Team Epsilon | 79 |  | 919 | 0 | 77828 | -0.31131 | (-inf, -0.2] | (30.0, inf] | 33
INIT0074 | Analytics Suite - Feature 74 | Analytics Suite | In Development | 2023-08-08 | 2023-10-20 |  | 15 | 50000 | 27528 | 74 | Medium | 5000000 |  | 50 | Team Gamma | 73 |  | 741 | 0 | 22472 | -0.44944 | (-inf, -0.2] | (30.0, inf] | 217
INIT0075 | API - Feature 75 | API | Testing | 2023-09-03 | 2024-01-29 |  | 7 | 500000 | 293496 | 91 | High | 100000 |  | 80 | Team Gamma | 148 |  | 640 | 0 | 206504 | -0.41301 | (-inf, -0.2] | (30.0, inf] | 243
INIT0076 | Web Platform - Feature 76 | Web Platform | On Hold | 2023-03-13 | 2023-08-27 |  | 13 | 100000 | 51058 | 64 | Critical | 100000 |  | 25 | Team Gamma | 167 |  | 795 | 0 | 48942 | -0.48942 | (-inf, -0.2] | (30.0, inf] | 69
INIT0077 | Mobile App - Feature 77 | Mobile App | On Hold | 2023-10-24 | 2024-03-05 |  | 3 | 1000000 | 470208 | 95 | Critical | 1000000 |  | 25 | Team Epsilon | 133 |  | 604 | 0 | 529792 | -0.52979 | (-inf, -0.2] | (30.0, inf] | 294
INIT0078 | Analytics Suite - Feature 78 | Analytics Suite | On Hold | 2023-07-07 | 2023-11-14 |  | 12 | 100000 | 101315 | 78 | Low | 500000 |  | 25 | Team Beta | 130 |  | 716 | 0 | -1315 | 0.01315 | (0.0, 0.1] | (30.0, inf] | 185
INIT0079 | Data Infrastructure - Feature 79 | Data Infrastructure | On Hold | 2023-07-06 | 2023-12-11 |  | 15 | 50000 | 41507 | 99 | Critical | 500000 |  | 25 | Team Delta | 158 |  | 689 | 0 | 8493 | -0.16986 | (-0.2, -0.1] | (30.0, inf] | 184
INIT0080 | Analytics Suite - Feature 80 | Analytics Suite | In Development | 2023-04-02 | 2023-09-23 |  | 5 | 1000000 | 827530 | 90 | Low | 1000000 |  | 50 | Team Beta | 174 |  | 768 | 0 | 172470 | -0.17247 | (-0.2, -0.1] | (30.0, inf] | 89

## Dashboard
Status Overview
In Development | 13
Launched | 18
On Hold | 15
Planning | 18
Testing | 16
On-time delivery rate | 33.33%
Budget utilization rate | 72.26%
Average resource utilization | 81.28%
Total expected revenue | 104200000
Total actual revenue | 21409447

## Budget_Performance
Initiative | Product_Line | Budget Allocated | Budget Spent | Variance Amount | Variance %
Analytics Suite - Feature 1 | Analytics Suite | 1000000 | 617883 | 382117 | -38.21%
Mobile App - Feature 2 | Mobile App | 100000 | 75327 | 24673 | -24.67%
Analytics Suite - Feature 3 | Analytics Suite | 250000 | 151608 | 98392 | -39.36%
Mobile App - Feature 4 | Mobile App | 50000 | 30831 | 19169 | -38.34%
Data Infrastructure - Feature 5 | Data Infrastructure | 250000 | 131069 | 118931 | -47.57%
Web Platform - Feature 6 | Web Platform | 1000000 | 816443 | 183557 | -18.36%
Data Infrastructure - Feature 7 | Data Infrastructure | 500000 | 204259 | 295741 | -59.15%
Web Platform - Feature 8 | Web Platform | 250000 | 215926 | 34074 | -13.63%
Analytics Suite - Feature 9 | Analytics Suite | 100000 | 106841 | -6841 | 6.841%
API - Feature 10 | API | 100000 | 98305 | 1695 | -1.695%
Web Platform - Feature 11 | Web Platform | 50000 | 33963 | 16037 | -32.07%
Web Platform - Feature 12 | Web Platform | 250000 | 166799 | 83201 | -33.28%
Analytics Suite - Feature 13 | Analytics Suite | 1000000 | 1099543 | -99543 | 9.954%
API - Feature 14 | API | 250000 | 247298 | 2702 | -1.081%
Web Platform - Feature 15 | Web Platform | 250000 | 211151 | 38849 | -15.54%
API - Feature 16 | API | 1000000 | 866455 | 133545 | -13.35%
Web Platform - Feature 17 | Web Platform | 100000 | 97251 | 2749 | -2.749%
Mobile App - Feature 18 | Mobile App | 50000 | 23890 | 26110 | -52.22%
API - Feature 19 | API | 50000 | 33821 | 16179 | -32.36%
Data Infrastructure - Feature 20 | Data Infrastructure | 500000 | 171624 | 328376 | -65.68%
API - Feature 21 | API | 250000 | 201206 | 48794 | -19.52%
API - Feature 22 | API | 50000 | 20176 | 29824 | -59.65%
Data Infrastructure - Feature 23 | Data Infrastructure | 50000 | 50680 | -680 | 1.36%
Mobile App - Feature 24 | Mobile App | 50000 | 30342 | 19658 | -39.32%
Mobile App - Feature 25 | Mobile App | 1000000 | 719294 | 280706 | -28.07%
Data Infrastructure - Feature 26 | Data Infrastructure | 100000 | 47945 | 52055 | -52.05%
Analytics Suite - Feature 27 | Analytics Suite | 500000 | 500617 | -617 | 0.1234%
Analytics Suite - Feature 28 | Analytics Suite | 500000 | 327725 | 172275 | -34.46%
Data Infrastructure - Feature 29 | Data Infrastructure | 50000 | 41499 | 8501 | -17%
Data Infrastructure - Feature 30 | Data Infrastructure | 500000 | 229458 | 270542 | -54.11%
API - Feature 31 | API | 500000 | 282241 | 217759 | -43.55%
Analytics Suite - Feature 32 | Analytics Suite | 250000 | 203867 | 46133 | -18.45%
Mobile App - Feature 33 | Mobile App | 500000 | 445416 | 54584 | -10.92%
Web Platform - Feature 34 | Web Platform | 50000 | 29904 | 20096 | -40.19%
Data Infrastructure - Feature 35 | Data Infrastructure | 100000 | 39044 | 60956 | -60.96%
Analytics Suite - Feature 36 | Analytics Suite | 50000 | 49503 | 497 | -0.994%
Mobile App - Feature 37 | Mobile App | 1000000 | 914022 | 85978 | -8.598%
API - Feature 38 | API | 500000 | 288299 | 211701 | -42.34%
Analytics Suite - Feature 39 | Analytics Suite | 1000000 | 979076 | 20924 | -2.092%
Data Infrastructure - Feature 40 | Data Infrastructure | 1000000 | 478165 | 521835 | -52.18%
Web Platform - Feature 41 | Web Platform | 50000 | 49263 | 737 | -1.474%
Data Infrastructure - Feature 42 | Data Infrastructure | 1000000 | 739279 | 260721 | -26.07%
Analytics Suite - Feature 43 | Analytics Suite | 50000 | 47663 | 2337 | -4.674%
API - Feature 44 | API | 250000 | 184538 | 65462 | -26.18%
Data Infrastructure - Feature 45 | Data Infrastructure | 100000 | 39659 | 60341 | -60.34%
Web Platform - Feature 46 | Web Platform | 50000 | 45885 | 4115 | -8.23%
Data Infrastructure - Feature 47 | Data Infrastructure | 500000 | 519748 | -19748 | 3.95%
Web Platform - Feature 48 | Web Platform | 1000000 | 1005112 | -5112 | 0.5112%
API - Feature 49 | API | 1000000 | 539130 | 460870 | -46.09%
Analytics Suite - Feature 50 | Analytics Suite | 250000 | 259238 | -9238 | 3.695%
Mobile App - Feature 51 | Mobile App | 1000000 | 528742 | 471258 | -47.13%
Mobile App - Feature 52 | Mobile App | 250000 | 211678 | 38322 | -15.33%
Analytics Suite - Feature 53 | Analytics Suite | 100000 | 89393 | 10607 | -10.61%
Analytics Suite - Feature 54 | Analytics Suite | 250000 | 268166 | -18166 | 7.266%
Web Platform - Feature 55 | Web Platform | 1000000 | 737292 | 262708 | -26.27%
API - Feature 56 | API | 500000 | 166253 | 333747 | -66.75%
Analytics Suite - Feature 57 | Analytics Suite | 50000 | 21148 | 28852 | -57.7%
Analytics Suite - Feature 58 | Analytics Suite | 50000 | 46361 | 3639 | -7.278%
Web Platform - Feature 59 | Web Platform | 1000000 | 729628 | 270372 | -27.04%
Web Platform - Feature 60 | Web Platform | 1000000 | 724399 | 275601 | -27.56%
API - Feature 61 | API | 250000 | 151274 | 98726 | -39.49%
API - Feature 62 | API | 500000 | 167540 | 332460 | -66.49%
Analytics Suite - Feature 63 | Analytics Suite | 50000 | 40077 | 9923 | -19.85%
Data Infrastructure - Feature 64 | Data Infrastructure | 50000 | 44875 | 5125 | -10.25%
API - Feature 65 | API | 250000 | 186616 | 63384 | -25.35%
Data Infrastructure - Feature 66 | Data Infrastructure | 50000 | 36393 | 13607 | -27.21%
Analytics Suite - Feature 67 | Analytics Suite | 250000 | 232378 | 17622 | -7.049%
API - Feature 68 | API | 100000 | 40910 | 59090 | -59.09%
Web Platform - Feature 69 | Web Platform | 100000 | 39858 | 60142 | -60.14%
Analytics Suite - Feature 70 | Analytics Suite | 100000 | 63012 | 36988 | -36.99%
Web Platform - Feature 71 | Web Platform | 50000 | 22254 | 27746 | -55.49%
Analytics Suite - Feature 72 | Analytics Suite | 1000000 | 689752 | 310248 | -31.02%
Web Platform - Feature 73 | Web Platform | 250000 | 172172 | 77828 | -31.13%
Analytics Suite - Feature 74 | Analytics Suite | 50000 | 27528 | 22472 | -44.94%
API - Feature 75 | API | 500000 | 293496 | 206504 | -41.3%
Web Platform - Feature 76 | Web Platform | 100000 | 51058 | 48942 | -48.94%
Mobile App - Feature 77 | Mobile App | 1000000 | 470208 | 529792 | -52.98%
Analytics Suite - Feature 78 | Analytics Suite | 100000 | 101315 | -1315 | 1.315%
Data Infrastructure - Feature 79 | Data Infrastructure | 50000 | 41507 | 8493 | -16.99%
Analytics Suite - Feature 80 | Analytics Suite | 1000000 | 827530 | 172470 | -17.25%
Product Line | Allocated | Spent
API | 6050000 | 3767558
Analytics Suite | 7950000 | 6750224
Data Infrastructure | 4800000 | 2815204
Mobile App | 5000000 | 3449750
Web Platform | 6550000 | 5148358

## Resource_Allocation
Team Name | Allocated Resources | Avg Utilization
Team Alpha | 188 | 80.81%
Team Beta | 67 | 76.89%
Team Delta | 143 | 83.13%
Team Epsilon | 144 | 85.47%
Team Gamma | 191 | 79.2%

## Delivery_Performance
Initiative | Planned Duration | Actual Duration | Budget Var % | Schedule Var (days) | Budget Allocated
Analytics Suite - Feature 1 | 129 |  | -38.21% | 860 | 1000000
Mobile App - Feature 2 | 68 |  | -24.67% | 753 | 100000
Analytics Suite - Feature 3 | 135 |  | -39.36% | 722 | 250000
Mobile App - Feature 4 | 132 |  | -38.34% | 828 | 50000
Data Infrastructure - Feature 5 | 107 |  | -47.57% | 754 | 250000
Web Platform - Feature 6 | 136 |  | -18.36% | 760 | 1000000
Data Infrastructure - Feature 7 | 70 | 73 | -59.15% | 3 | 500000
Web Platform - Feature 8 | 42 |  | -13.63% | 758 | 250000
Analytics Suite - Feature 9 | 125 | 127 | 6.841% | 2 | 100000
API - Feature 10 | 42 |  | -1.695% | 794 | 100000
Web Platform - Feature 11 | 35 |  | -32.07% | 736 | 50000
Web Platform - Feature 12 | 126 |  | -33.28% | 691 | 250000
Analytics Suite - Feature 13 | 31 |  | 9.954% | 950 | 1000000
API - Feature 14 | 100 |  | -1.081% | 761 | 250000
Web Platform - Feature 15 | 133 |  | -15.54% | 593 | 250000
API - Feature 16 | 39 |  | -13.35% | 796 | 1000000
Web Platform - Feature 17 | 106 |  | -2.749% | 668 | 100000
Mobile App - Feature 18 | 76 | 102 | -52.22% | 26 | 50000
API - Feature 19 | 148 |  | -32.36% | 735 | 50000
Data Infrastructure - Feature 20 | 106 |  | -65.68% | 656 | 500000
API - Feature 21 | 76 | 112 | -19.52% | 36 | 250000
API - Feature 22 | 155 |  | -59.65% | 797 | 50000
Data Infrastructure - Feature 23 | 39 | 39 | 1.36% | 0 | 50000
Mobile App - Feature 24 | 63 |  | -39.32% | 811 | 50000
Mobile App - Feature 25 | 163 |  | -28.07% | 637 | 1000000
Data Infrastructure - Feature 26 | 34 |  | -52.05% | 793 | 100000
Analytics Suite - Feature 27 | 39 |  | 0.1234% | 807 | 500000
Analytics Suite - Feature 28 | 59 |  | -34.46% | 950 | 500000
Data Infrastructure - Feature 29 | 137 |  | -17% | 742 | 50000
Data Infrastructure - Feature 30 | 57 |  | -54.11% | 918 | 500000
API - Feature 31 | 170 | 168 | -43.55% | -2 | 500000
Analytics Suite - Feature 32 | 49 | 60 | -18.45% | 11 | 250000
Mobile App - Feature 33 | 110 |  | -10.92% | 739 | 500000
Web Platform - Feature 34 | 98 |  | -40.19% | 711 | 50000
Data Infrastructure - Feature 35 | 152 | 198 | -60.96% | 46 | 100000
Analytics Suite - Feature 36 | 127 | 171 | -0.994% | 44 | 50000
Mobile App - Feature 37 | 96 | 91 | -8.598% | -5 | 1000000
API - Feature 38 | 93 |  | -42.34% | 602 | 500000
Analytics Suite - Feature 39 | 70 |  | -2.092% | 634 | 1000000
Data Infrastructure - Feature 40 | 42 |  | -52.18% | 849 | 1000000
Web Platform - Feature 41 | 144 |  | -1.474% | 596 | 50000
Data Infrastructure - Feature 42 | 39 |  | -26.07% | 783 | 1000000
Analytics Suite - Feature 43 | 123 |  | -4.674% | 736 | 50000
API - Feature 44 | 86 | 86 | -26.18% | 0 | 250000
Data Infrastructure - Feature 45 | 80 |  | -60.34% | 823 | 100000
Web Platform - Feature 46 | 180 |  | -8.23% | 830 | 50000
Data Infrastructure - Feature 47 | 179 |  | 3.95% | 633 | 500000
Web Platform - Feature 48 | 112 |  | 0.5112% | 611 | 1000000
API - Feature 49 | 64 | 68 | -46.09% | 4 | 1000000
Analytics Suite - Feature 50 | 104 |  | 3.695% | 610 | 250000
Mobile App - Feature 51 | 136 |  | -47.13% | 605 | 1000000
Mobile App - Feature 52 | 44 | 41 | -15.33% | -3 | 250000
Analytics Suite - Feature 53 | 173 |  | -10.61% | 808 | 100000
Analytics Suite - Feature 54 | 136 |  | 7.266% | 699 | 250000
Web Platform - Feature 55 | 124 |  | -26.27% | 585 | 1000000
API - Feature 56 | 74 | 86 | -66.75% | 12 | 500000
Analytics Suite - Feature 57 | 69 |  | -57.7% | 726 | 50000
Analytics Suite - Feature 58 | 121 |  | -7.278% | 631 | 50000
Web Platform - Feature 59 | 136 |  | -27.04% | 816 | 1000000
Web Platform - Feature 60 | 85 |  | -27.56% | 798 | 1000000
API - Feature 61 | 92 | 140 | -39.49% | 48 | 250000
API - Feature 62 | 144 |  | -66.49% | 629 | 500000
Analytics Suite - Feature 63 | 166 |  | -19.85% | 592 | 50000
Data Infrastructure - Feature 64 | 141 |  | -10.25% | 533 | 50000
API - Feature 65 | 75 |  | -25.35% | 931 | 250000
Data Infrastructure - Feature 66 | 110 | 115 | -27.21% | 5 | 50000
Analytics Suite - Feature 67 | 57 |  | -7.049% | 719 | 250000
API - Feature 68 | 37 | 40 | -59.09% | 3 | 100000
Web Platform - Feature 69 | 172 |  | -60.14% | 578 | 100000
Analytics Suite - Feature 70 | 118 |  | -36.99% | 808 | 100000
Web Platform - Feature 71 | 79 |  | -55.49% | 825 | 50000
Analytics Suite - Feature 72 | 47 | 45 | -31.02% | -2 | 1000000
Web Platform - Feature 73 | 79 |  | -31.13% | 919 | 250000
Analytics Suite - Feature 74 | 73 |  | -44.94% | 741 | 50000
API - Feature 75 | 148 |  | -41.3% | 640 | 500000
Web Platform - Feature 76 | 167 |  | -48.94% | 795 | 100000
Mobile App - Feature 77 | 133 |  | -52.98% | 604 | 1000000
Analytics Suite - Feature 78 | 130 |  | 1.315% | 716 | 100000
Data Infrastructure - Feature 79 | 158 |  | -16.99% | 689 | 50000
Analytics Suite - Feature 80 | 174 |  | -17.25% | 768 | 1000000
Initiative | Planned | Actual | Budget Allocated
Data Infrastructure - Feature 23 | 39 | 39 | 50000
API - Feature 31 | 170 | 168 | 500000
Mobile App - Feature 37 | 96 | 91 | 1000000
API - Feature 44 | 86 | 86 | 250000
Mobile App - Feature 52 | 44 | 41 | 250000
Analytics Suite - Feature 72 | 47 | 45 | 1000000
Analytics Suite - Feature 1 | 129 | 0 | 1000000
Mobile App - Feature 2 | 68 | 0 | 100000
Analytics Suite - Feature 3 | 135 | 0 | 250000
Mobile App - Feature 4 | 132 | 0 | 50000
Data Infrastructure - Feature 5 | 107 | 0 | 250000
Web Platform - Feature 6 | 136 | 0 | 1000000
Data Infrastructure - Feature 7 | 70 | 73 | 500000
Web Platform - Feature 8 | 42 | 0 | 250000
Analytics Suite - Feature 9 | 125 | 127 | 100000
API - Feature 10 | 42 | 0 | 100000
Web Platform - Feature 11 | 35 | 0 | 50000
Web Platform - Feature 12 | 126 | 0 | 250000
Analytics Suite - Feature 13 | 31 | 0 | 1000000
API - Feature 14 | 100 | 0 | 250000
Web Platform - Feature 15 | 133 | 0 | 250000
API - Feature 16 | 39 | 0 | 1000000
Web Platform - Feature 17 | 106 | 0 | 100000
Mobile App - Feature 18 | 76 | 102 | 50000
API - Feature 19 | 148 | 0 | 50000
Data Infrastructure - Feature 20 | 106 | 0 | 500000
API - Feature 21 | 76 | 112 | 250000
API - Feature 22 | 155 | 0 | 50000
Mobile App - Feature 24 | 63 | 0 | 50000
Mobile App - Feature 25 | 163 | 0 | 1000000
Data Infrastructure - Feature 26 | 34 | 0 | 100000
Analytics Suite - Feature 27 | 39 | 0 | 500000
Analytics Suite - Feature 28 | 59 | 0 | 500000
Data Infrastructure - Feature 29 | 137 | 0 | 50000
Data Infrastructure - Feature 30 | 57 | 0 | 500000
Analytics Suite - Feature 32 | 49 | 60 | 250000
Mobile App - Feature 33 | 110 | 0 | 500000
Web Platform - Feature 34 | 98 | 0 | 50000
Data Infrastructure - Feature 35 | 152 | 198 | 100000
Analytics Suite - Feature 36 | 127 | 171 | 50000
API - Feature 38 | 93 | 0 | 500000
Analytics Suite - Feature 39 | 70 | 0 | 1000000
Data Infrastructure - Feature 40 | 42 | 0 | 1000000
Web Platform - Feature 41 | 144 | 0 | 50000
Data Infrastructure - Feature 42 | 39 | 0 | 1000000
Analytics Suite - Feature 43 | 123 | 0 | 50000
Data Infrastructure - Feature 45 | 80 | 0 | 100000
Web Platform - Feature 46 | 180 | 0 | 50000
Data Infrastructure - Feature 47 | 179 | 0 | 500000
Web Platform - Feature 48 | 112 | 0 | 1000000
API - Feature 49 | 64 | 68 | 1000000
Analytics Suite - Feature 50 | 104 | 0 | 250000
Mobile App - Feature 51 | 136 | 0 | 1000000
Analytics Suite - Feature 53 | 173 | 0 | 100000
Analytics Suite - Feature 54 | 136 | 0 | 250000
Web Platform - Feature 55 | 124 | 0 | 1000000
API - Feature 56 | 74 | 86 | 500000
Analytics Suite - Feature 57 | 69 | 0 | 50000
Analytics Suite - Feature 58 | 121 | 0 | 50000
Web Platform - Feature 59 | 136 | 0 | 1000000
Web Platform - Feature 60 | 85 | 0 | 1000000
API - Feature 61 | 92 | 140 | 250000
API - Feature 62 | 144 | 0 | 500000
Analytics Suite - Feature 63 | 166 | 0 | 50000
Data Infrastructure - Feature 64 | 141 | 0 | 50000
API - Feature 65 | 75 | 0 | 250000
Data Infrastructure - Feature 66 | 110 | 115 | 50000
Analytics Suite - Feature 67 | 57 | 0 | 250000
API - Feature 68 | 37 | 40 | 100000
Web Platform - Feature 69 | 172 | 0 | 100000
Analytics Suite - Feature 70 | 118 | 0 | 100000
Web Platform - Feature 71 | 79 | 0 | 50000
Web Platform - Feature 73 | 79 | 0 | 250000
Analytics Suite - Feature 74 | 73 | 0 | 50000
API - Feature 75 | 148 | 0 | 500000
Web Platform - Feature 76 | 167 | 0 | 100000
Mobile App - Feature 77 | 133 | 0 | 1000000
Analytics Suite - Feature 78 | 130 | 0 | 100000
Data Infrastructure - Feature 79 | 158 | 0 | 50000
Analytics Suite - Feature 80 | 174 | 0 | 1000000

## Revenue_Impact
Initiative | Expected Revenue | Actual Revenue | Difference
Analytics Suite - Feature 1 | 5000000
Analytics Suite - Feature 3 | 5000000
Analytics Suite - Feature 36 | 5000000 | 5721392 | 721392
Analytics Suite - Feature 74 | 5000000
Data Infrastructure - Feature 40 | 5000000
Web Platform - Feature 69 | 5000000
Web Platform - Feature 8 | 5000000
Mobile App - Feature 18 | 5000000 | 5258316 | 258316
Analytics Suite - Feature 43 | 5000000
Data Infrastructure - Feature 64 | 5000000
API - Feature 22 | 5000000
API - Feature 61 | 5000000 | 3398066 | -1601934
Data Infrastructure - Feature 45 | 5000000
Web Platform - Feature 15 | 5000000
API - Feature 49 | 1000000 | 998312 | -1688
Data Infrastructure - Feature 42 | 1000000
Analytics Suite - Feature 50 | 1000000
API - Feature 56 | 1000000 | 591046 | -408954
Mobile App - Feature 52 | 1000000 | 642800 | -357200
Analytics Suite - Feature 54 | 1000000
Analytics Suite - Feature 28 | 1000000
API - Feature 62 | 1000000
API - Feature 65 | 1000000
API - Feature 68 | 1000000 | 1172093 | 172093
Web Platform - Feature 73 | 1000000
Mobile App - Feature 77 | 1000000
Analytics Suite - Feature 32 | 1000000 | 824994 | -175006
Analytics Suite - Feature 80 | 1000000
Mobile App - Feature 25 | 1000000
API - Feature 16 | 1000000
Analytics Suite - Feature 13 | 1000000
Analytics Suite - Feature 9 | 1000000 | 740974 | -259026
Web Platform - Feature 12 | 1000000
Web Platform - Feature 17 | 1000000
Data Infrastructure - Feature 29 | 500000
Data Infrastructure - Feature 30 | 500000
API - Feature 14 | 500000
Analytics Suite - Feature 58 | 500000
Web Platform - Feature 59 | 500000
Analytics Suite - Feature 63 | 500000
API - Feature 10 | 500000
Analytics Suite - Feature 70 | 500000
Analytics Suite - Feature 72 | 500000 | 484953 | -15047
Web Platform - Feature 6 | 500000
Data Infrastructure - Feature 5 | 500000
Analytics Suite - Feature 78 | 500000
Data Infrastructure - Feature 79 | 500000
Analytics Suite - Feature 53 | 500000
Web Platform - Feature 55 | 500000
API - Feature 38 | 500000
Web Platform - Feature 46 | 500000
Data Infrastructure - Feature 35 | 500000 | 286299 | -213701
Mobile App - Feature 24 | 500000
Data Infrastructure - Feature 23 | 500000 | 256270 | -243730
Data Infrastructure - Feature 47 | 500000
Web Platform - Feature 48 | 500000
Data Infrastructure - Feature 20 | 500000
Mobile App - Feature 37 | 500000 | 592263 | 92263
API - Feature 31 | 100000 | 113481 | 13481
Analytics Suite - Feature 27 | 100000
Mobile App - Feature 4 | 100000
Data Infrastructure - Feature 7 | 100000 | 62161 | -37839
Web Platform - Feature 76 | 100000
API - Feature 75 | 100000
Mobile App - Feature 33 | 100000
Web Platform - Feature 34 | 100000
Web Platform - Feature 71 | 100000
Data Infrastructure - Feature 26 | 100000
API - Feature 19 | 100000
Analytics Suite - Feature 67 | 100000
Data Infrastructure - Feature 66 | 100000 | 102917 | 2917
Mobile App - Feature 51 | 100000
Web Platform - Feature 11 | 100000
Analytics Suite - Feature 39 | 100000
Mobile App - Feature 2 | 100000
Web Platform - Feature 60 | 100000
API - Feature 44 | 100000 | 112781 | 12781
Analytics Suite - Feature 57 | 100000
API - Feature 21 | 100000 | 50329 | -49671
Web Platform - Feature 41 | 100000

## Status_Waterfall
Product Line | In Development | Launched | On Hold | Planning | Testing
API | 0 | 7 | 0 | 4 | 3
Analytics Suite | 0 | 4 | 0 | 5 | 4
Data Infrastructure | 0 | 4 | 0 | 4 | 3
Mobile App | 0 | 3 | 0 | 1 | 1
Web Platform | 0 | 0 | 0 | 4 | 5

## Risk_Matrix
Schedule vs Budget Variance
| <-20% | -20% to -10% | -10% to 0 | 0 to +10% | +10% to +20% | >+20%
<-30d
-30 to -10d
-10 to 0
0 to 10d
10 to 30d
>30d

## Gantt_Chart
Initiative | Start Offset | Duration | Status | Start Date
Analytics Suite - Feature 1 | 42 | 129 | Testing | 2023-02-14
Mobile App - Feature 2 | 210 | 68 | On Hold | 2023-08-01
Analytics Suite - Feature 3 | 174 | 135 | Planning | 2023-06-26
Mobile App - Feature 4 | 71 | 132 | In Development | 2023-03-15
Data Infrastructure - Feature 5 | 170 | 107 | Testing | 2023-06-22
Web Platform - Feature 6 | 135 | 136 | Testing | 2023-05-18
Data Infrastructure - Feature 7 | 261 | 70 | Launched | 2023-09-21
Web Platform - Feature 8 | 231 | 42 | Planning | 2023-08-22
Analytics Suite - Feature 9 | 121 | 125 | Launched | 2023-05-04
API - Feature 10 | 195 | 42 | Planning | 2023-07-17
Web Platform - Feature 11 | 260 | 35 | In Development | 2023-09-20
Web Platform - Feature 12 | 214 | 126 | Testing | 2023-08-05
Analytics Suite - Feature 13 | 50 | 31 | On Hold | 2023-02-22
API - Feature 14 | 170 | 100 | Planning | 2023-06-22
Web Platform - Feature 15 | 305 | 133 | On Hold | 2023-11-04
API - Feature 16 | 196 | 39 | Testing | 2023-07-18
Web Platform - Feature 17 | 257 | 106 | On Hold | 2023-09-17
Mobile App - Feature 18 | 284 | 76 | Launched | 2023-10-14
API - Feature 19 | 148 | 148 | Testing | 2023-05-31
Data Infrastructure - Feature 20 | 269 | 106 | In Development | 2023-09-29
API - Feature 21 | 159 | 76 | Launched | 2023-06-11
API - Feature 22 | 79 | 155 | In Development | 2023-03-23
Data Infrastructure - Feature 23 | 0 | 39 | Launched | 2023-01-03
Mobile App - Feature 24 | 157 | 63 | In Development | 2023-06-09
Mobile App - Feature 25 | 231 | 163 | Planning | 2023-08-22
Data Infrastructure - Feature 26 | 204 | 34 | Testing | 2023-07-26
Analytics Suite - Feature 27 | 185 | 39 | On Hold | 2023-07-07
Analytics Suite - Feature 28 | 22 | 59 | Planning | 2023-01-25
Data Infrastructure - Feature 29 | 152 | 137 | In Development | 2023-06-04
Data Infrastructure - Feature 30 | 56 | 57 | Planning | 2023-02-28
API - Feature 31 | 18 | 170 | Launched | 2023-01-21
Analytics Suite - Feature 32 | 259 | 49 | Launched | 2023-09-19
Mobile App - Feature 33 | 182 | 110 | In Development | 2023-07-04
Web Platform - Feature 34 | 222 | 98 | In Development | 2023-08-13
Data Infrastructure - Feature 35 | 195 | 152 | Launched | 2023-07-17
Analytics Suite - Feature 36 | 310 | 127 | Launched | 2023-11-09
Mobile App - Feature 37 | 30 | 96 | Launched | 2023-02-02
API - Feature 38 | 336 | 93 | On Hold | 2023-12-05
Analytics Suite - Feature 39 | 327 | 70 | On Hold | 2023-11-26
Data Infrastructure - Feature 40 | 140 | 42 | Testing | 2023-05-23
Web Platform - Feature 41 | 291 | 144 | Planning | 2023-10-21
Data Infrastructure - Feature 42 | 209 | 39 | Planning | 2023-07-31
Analytics Suite - Feature 43 | 172 | 123 | On Hold | 2023-06-24
API - Feature 44 | 335 | 86 | Launched | 2023-12-04
Data Infrastructure - Feature 45 | 128 | 80 | In Development | 2023-05-11
Web Platform - Feature 46 | 21 | 180 | Testing | 2023-01-24
Data Infrastructure - Feature 47 | 219 | 179 | Planning | 2023-08-10
Web Platform - Feature 48 | 308 | 112 | Planning | 2023-11-07
API - Feature 49 | 229 | 64 | Launched | 2023-08-20
Analytics Suite - Feature 50 | 317 | 104 | In Development | 2023-11-16
Mobile App - Feature 51 | 290 | 136 | Testing | 2023-10-20
Mobile App - Feature 52 | 341 | 44 | Launched | 2023-12-10
Analytics Suite - Feature 53 | 50 | 173 | Planning | 2023-02-22
Analytics Suite - Feature 54 | 196 | 136 | Testing | 2023-07-18
Web Platform - Feature 55 | 322 | 124 | On Hold | 2023-11-21
API - Feature 56 | 93 | 74 | Launched | 2023-04-06
Analytics Suite - Feature 57 | 236 | 69 | Testing | 2023-08-27
Analytics Suite - Feature 58 | 279 | 121 | Testing | 2023-10-09
Web Platform - Feature 59 | 79 | 136 | On Hold | 2023-03-23
Web Platform - Feature 60 | 148 | 85 | Testing | 2023-05-31
API - Feature 61 | 316 | 92 | Launched | 2023-11-15
API - Feature 62 | 258 | 144 | Planning | 2023-09-18
Analytics Suite - Feature 63 | 273 | 166 | Planning | 2023-10-03
Data Infrastructure - Feature 64 | 357 | 141 | Planning | 2023-12-26
API - Feature 65 | 25 | 75 | Planning | 2023-01-28
Data Infrastructure - Feature 66 | 219 | 110 | Launched | 2023-08-10
Analytics Suite - Feature 67 | 255 | 57 | Planning | 2023-09-15
API - Feature 68 | 336 | 37 | Launched | 2023-12-05
Web Platform - Feature 69 | 281 | 172 | Testing | 2023-10-11
Analytics Suite - Feature 70 | 105 | 118 | On Hold | 2023-04-18
Web Platform - Feature 71 | 127 | 79 | In Development | 2023-05-10
Analytics Suite - Feature 72 | 341 | 47 | Launched | 2023-12-10
Web Platform - Feature 73 | 33 | 79 | Planning | 2023-02-05
Analytics Suite - Feature 74 | 217 | 73 | In Development | 2023-08-08
API - Feature 75 | 243 | 148 | Testing | 2023-09-03
Web Platform - Feature 76 | 69 | 167 | On Hold | 2023-03-13
Mobile App - Feature 77 | 294 | 133 | On Hold | 2023-10-24
Analytics Suite - Feature 78 | 185 | 130 | On Hold | 2023-07-07
Data Infrastructure - Feature 79 | 184 | 158 | On Hold | 2023-07-06
Analytics Suite - Feature 80 | 89 | 174 | In Development | 2023-04-02