## Raw_Data
Initiative_ID,Initiative_Name,Product_Line,Status,Start_Date,Target_Completion_Date,Actual_Completion_Date,Team_Size,Budget_Allocated,Budget_Spent,Resource_Utilization,Priority,Expected_Revenue_Impact,Actual_Revenue_Impact,Progress_Percentage,Assigned_Team
INIT0001,Analytics Suite - Feature 1,Analytics Suite,Testing,2023-02-14,2023-06-23,,8,1000000,617883,77,Medium,5000000,,80,Team Alpha
INIT0002,Mobile App - Feature 2,Mobile App,On Hold,2023-08-01,2023-10-08,,12,100000,75327,66,Low,100000,,25,Team Alpha
INIT0003,Analytics Suite - Feature 3,Analytics Suite,Planning,2023-06-26,2023-11-08,,10,250000,151608,96,Medium,5000000,,10,Team Epsilon
INIT0004,Mobile App - Feature 4,Mobile App,In Development,2023-03-15,2023-07-25,,8,50000,30831,75,Medium,100000,,50,Team Delta
INIT0005,Data Infrastructure - Feature 5,Data Infrastructure,Testing,2023-06-22,2023-10-07,,10,250000,131069,66,Medium,500000,,80,Team Alpha
INIT0006,Web Platform - Feature 6,Web Platform,Testing,2023-05-18,2023-10-01,,6,1000000,816443,88,Low,500000,,80,Team Gamma
INIT0007,Data Infrastructure - Feature 7,Data Infrastructure,Launched,2023-09-21,2023-11-30,2023-12-03,11,500000,204259,96,Medium,100000,62161,100,Team Alpha
INIT0008,Web Platform - Feature 8,Web Platform,Planning,2023-08-22,2023-10-03,,7,250000,215926,83,High,5000000,,10,Team Alpha
INIT0009,Analytics Suite - Feature 9,Analytics Suite,Launched,2023-05-04,2023-09-06,2023-09-08,10,100000,106841,97,Critical,1000000,740974,100,Team Alpha
INIT0010,API - Feature 10,API,Planning,2023-07-17,2023-08-28,,15,100000,98305,73,Medium,500000,,10,Team Alpha
INIT0011,Web Platform - Feature 11,Web Platform,In Development,2023-09-20,2023-10-25,,5,50000,33963,71,Medium,100000,,50,Team Delta
INIT0012,Web Platform - Feature 12,Web Platform,Testing,2023-08-05,2023-12-09,,6,250000,166799,89,Medium,1000000,,80,Team Gamma
INIT0013,Analytics Suite - Feature 13,Analytics Suite,On Hold,2023-02-22,2023-03-25,,8,1000000,1099543,95,Low,1000000,,25,Team Epsilon
INIT0014,API - Feature 14,API,Planning,2023-06-22,2023-09-30,,7,250000,247298,79,Low,500000,,10,Team Alpha
INIT0015,Web Platform - Feature 15,Web Platform,On Hold,2023-11-04,2024-03-16,,14,250000,211151,61,High,5000000,,25,Team Alpha
INIT0016,API - Feature 16,API,Testing,2023-07-18,2023-08-26,,12,1000000,866455,72,Low,1000000,,80,Team Delta
INIT0017,Web Platform - Feature 17,Web Platform,On Hold,2023-09-17,2024-01-01,,11,100000,97251,71,Low,1000000,,25,Team Gamma
INIT0018,Mobile App - Feature 18,Mobile App,Launched,2023-10-14,2023-12-29,2024-01-24,6,50000,23890,79,High,5000000,5258316,100,Team Gamma
INIT0019,API - Feature 19,API,Testing,2023-05-31,2023-10-26,,13,50000,33821,97,Medium,100000,,80,Team Epsilon
INIT0020,Data Infrastructure - Feature 20,Data Infrastructure,In Development,2023-09-29,2024-01-13,,5,500000,171624,68,Critical,500000,,50,Team Delta
INIT0021,API - Feature 21,API,Launched,2023-06-11,2023-08-26,2023-10-01,5,250000,201206,80,Low,100000,50329,100,Team Beta
INIT0022,API - Feature 22,API,In Development,2023-03-23,2023-08-25,,9,50000,20176,100,High,5000000,,50,Team Epsilon
INIT0023,Data Infrastructure - Feature 23,Data Infrastructure,Launched,2023-01-03,2023-02-11,2023-02-11,15,50000,50680,93,Low,500000,256270,100,Team Delta
INIT0024,Mobile App - Feature 24,Mobile App,In Development,2023-06-09,2023-08-11,,12,50000,30342,79,High,500000,,50,Team Gamma
INIT0025,Mobile App - Feature 25,Mobile App,Planning,2023-08-22,2024-02-01,,9,1000000,719294,68,Medium,1000000,,10,Team Gamma
INIT0026,Data Infrastructure - Feature 26,Data Infrastructure,Testing,2023-07-26,2023-08-29,,5,100000,47945,73,High,100000,,80,Team Beta
INIT0027,Analytics Suite - Feature 27,Analytics Suite,On Hold,2023-07-07,2023-08-15,,7,500000,500617,94,High,100000,,25,Team Alpha
INIT0028,Analytics Suite - Feature 28,Analytics Suite,Planning,2023-01-25,2023-03-25,,4,500000,327725,95,Critical,1000000,,10,Team Alpha
INIT0029,Data Infrastructure - Feature 29,Data Infrastructure,In Development,2023-06-04,2023-10-19,,7,50000,41499,99,High,500000,,50,Team Alpha
INIT0030,Data Infrastructure - Feature 30,Data Infrastructure,Planning,2023-02-28,2023-04-26,,6,500000,229458,76,Critical,500000,,10,Team Gamma
INIT0031,API - Feature 31,API,Launched,2023-01-21,2023-07-10,2023-07-08,3,500000,282241,60,Medium,100000,113481,100,Team Beta
INIT0032,Analytics Suite - Feature 32,Analytics Suite,Launched,2023-09-19,2023-11-07,2023-11-18,10,250000,203867,78,High,1000000,824994,100,Team Alpha
INIT0033,Mobile App - Feature 33,Mobile App,In Development,2023-07-04,2023-10-22,,4,500000,445416,62,Critical,100000,,50,Team Gamma
INIT0034,Web Platform - Feature 34,Web Platform,In Development,2023-08-13,2023-11-19,,8,50000,29904,71,Medium,100000,,50,Team Gamma
INIT0035,Data Infrastructure - Feature 35,Data Infrastructure,Launched,2023-07-17,2023-12-16,2024-01-31,14,100000,39044,63,Low,500000,286299,100,Team Gamma
INIT0036,Analytics Suite - Feature 36,Analytics Suite,Launched,2023-11-09,2024-03-15,2024-04-28,14,50000,49503,68,Low,5000000,5721392,100,Team Beta
INIT0037,Mobile App - Feature 37,Mobile App,Launched,2023-02-02,2023-05-09,2023-05-04,12,1000000,914022,96,Low,500000,592263,100,Team Alpha
INIT0038,API - Feature 38,API,On Hold,2023-12-05,2024-03-07,,13,500000,288299,84,Critical,500000,,25,Team Delta
INIT0039,Analytics Suite - Feature 39,Analytics Suite,On Hold,2023-11-26,2024-02-04,,10,1000000,979076,70,Critical,100000,,25,Team Alpha
INIT0040,Data Infrastructure - Feature 40,Data Infrastructure,Testing,2023-05-23,2023-07-04,,13,1000000,478165,84,High,5000000,,80,Team Gamma
INIT0041,Web Platform - Feature 41,Web Platform,Planning,2023-10-21,2024-03-13,,10,50000,49263,80,Low,100000,,10,Team Delta
INIT0042,Data Infrastructure - Feature 42,Data Infrastructure,Planning,2023-07-31,2023-09-08,,4,1000000,739279,98,Critical,1000000,,10,Team Delta
INIT0043,Analytics Suite - Feature 43,Analytics Suite,On Hold,2023-06-24,2023-10-25,,10,50000,47663,81,High,5000000,,25,Team Delta
INIT0044,API - Feature 44,API,Launched,2023-12-04,2024-02-28,2024-02-28,8,250000,184538,66,Critical,100000,112781,100,Team Alpha
INIT0045,Data Infrastructure - Feature 45,Data Infrastructure,In Development,2023-05-11,2023-07-30,,9,100000,39659,73,Low,5000000,,50,Team Alpha
INIT0046,Web Platform - Feature 46,Web Platform,Testing,2023-01-24,2023-07-23,,10,50000,45885,89,Critical,500000,,80,Team Delta
INIT0047,Data Infrastructure - Feature 47,Data Infrastructure,Planning,2023-08-10,2024-02-05,,15,500000,519748,71,Critical,500000,,10,Team Epsilon
INIT0048,Web Platform - Feature 48,Web Platform,Planning,2023-11-07,2024-02-27,,9,1000000,1005112,98,Low,500000,,10,Team Epsilon
INIT0049,API - Feature 49,API,Launched,2023-08-20,2023-10-23,2023-10-27,14,1000000,539130,95,Medium,1000000,998312,100,Team Gamma
INIT0050,Analytics Suite - Feature 50,Analytics Suite,In Development,2023-11-16,2024-02-28,,5,250000,259238,71,High,1000000,,50,Team Beta
INIT0051,Mobile App - Feature 51,Mobile App,Testing,2023-10-20,2024-03-04,,9,1000000,528742,60,Low,100000,,80,Team Epsilon
INIT0052,Mobile App - Feature 52,Mobile App,Launched,2023-12-10,2024-01-23,2024-01-20,5,250000,211678,63,High,1000000,642800,100,Team Alpha
INIT0053,Analytics Suite - Feature 53,Analytics Suite,Planning,2023-02-22,2023-08-14,,11,100000,89393,84,Medium,500000,,10,Team Delta
INIT0054,Analytics Suite - Feature 54,Analytics Suite,Testing,2023-07-18,2023-12-01,,3,250000,268166,60,Critical,1000000,,80,Team Delta
INIT0055,Web Platform - Feature 55,Web Platform,On Hold,2023-11-21,2024-03-24,,12,1000000,737292,72,Low,500000,,25,Team Beta
INIT0056,API - Feature 56,API,Launched,2023-04-06,2023-06-19,2023-07-01,7,500000,166253,95,High,1000000,591046,100,Team Alpha
INIT0057,Analytics Suite - Feature 57,Analytics Suite,Testing,2023-08-27,2023-11-04,,8,50000,21148,98,Critical,100000,,80,Team Gamma
INIT0058,Analytics Suite - Feature 58,Analytics Suite,Testing,2023-10-09,2024-02-07,,8,50000,46361,93,Low,500000,,80,Team Epsilon
INIT0059,Web Platform - Feature 59,Web Platform,On Hold,2023-03-23,2023-08-06,,4,1000000,729628,82,Critical,500000,,25,Team Epsilon
INIT0060,Web Platform - Feature 60,Web Platform,Testing,2023-05-31,2023-08-24,,11,1000000,724399,60,Medium,100000,,80,Team Gamma
INIT0061,API - Feature 61,API,Launched,2023-11-15,2024-02-15,2024-04-03,15,250000,151274,67,High,5000000,3398066,100,Team Epsilon
INIT0062,API - Feature 62,API,Planning,2023-09-18,2024-02-09,,13,500000,167540,72,Medium,1000000,,10,Team Epsilon
INIT0063,Analytics Suite - Feature 63,Analytics Suite,Planning,2023-10-03,2024-03-17,,6,50000,40077,100,Critical,500000,,10,Team Beta
INIT0064,Data Infrastructure - Feature 64,Data Infrastructure,Planning,2023-12-26,2024-05-15,,5,50000,44875,61,High,5000000,,10,Team Epsilon
INIT0065,API - Feature 65,API,Planning,2023-01-28,2023-04-13,,12,250000,186616,74,Critical,1000000,,10,Team Alpha
INIT0066,Data Infrastructure - Feature 66,Data Infrastructure,Launched,2023-08-10,2023-11-28,2023-12-03,13,50000,36393,99,Low,100000,102917,100,Team Delta
INIT0067,Analytics Suite - Feature 67,Analytics Suite,Planning,2023-09-15,2023-11-11,,7,250000,232378,98,Critical,100000,,10,Team Gamma
INIT0068,API - Feature 68,API,Launched,2023-12-05,2024-01-11,2024-01-14,9,100000,40910,94,Low,1000000,1172093,100,Team Delta
INIT0069,Web Platform - Feature 69,Web Platform,Testing,2023-10-11,2024-03-31,,3,100000,39858,96,Medium,5000000,,80,Team Alpha
INIT0070,Analytics Suite - Feature 70,Analytics Suite,On Hold,2023-04-18,2023-08-14,,13,100000,63012,92,Critical,500000,,25,Team Gamma
INIT0071,Web Platform - Feature 71,Web Platform,In Development,2023-05-10,2023-07-28,,15,50000,22254,96,High,100000,,50,Team Epsilon
INIT0072,Analytics Suite - Feature 72,Analytics Suite,Launched,2023-12-10,2024-01-26,2024-01-24,8,1000000,689752,82,Critical,500000,484953,100,Team Gamma
INIT0073,Web Platform - Feature 73,Web Platform,Planning,2023-02-05,2023-04-25,,8,250000,172172,99,Medium,1000000,,10,Team Epsilon
INIT0074,Analytics Suite - Feature 74,Analytics Suite,In Development,2023-08-08,2023-10-20,,15,50000,27528,74,Medium,5000000,,50,Team Gamma
INIT0075,API - Feature 75,API,Testing,2023-09-03,2024-01-29,,7,500000,293496,91,High,100000,,80,Team Gamma
INIT0076,Web Platform - Feature 76,Web Platform,On Hold,2023-03-13,2023-08-27,,13,100000,51058,64,Critical,100000,,25,Team Gamma
INIT0077,Mobile App - Feature 77,Mobile App,On Hold,2023-10-24,2024-03-05,,3,1000000,470208,95,Critical,1000000,,25,Team Epsilon
INIT0078,Analytics Suite - Feature 78,Analytics Suite,On Hold,2023-07-07,2023-11-14,,12,100000,101315,78,Low,500000,,25,Team Beta
INIT0079,Data Infrastructure - Feature 79,Data Infrastructure,On Hold,2023-07-06,2023-12-11,,15,50000,41507,99,Critical,500000,,25,Team Delta
INIT0080,Analytics Suite - Feature 80,Analytics Suite,In Development,2023-04-02,2023-09-23,,5,1000000,827530,90,Low,1000000,,50,Team Beta

## Data
Initiative_ID | Initiative_Name | Product_Line | Status | Start_Date | Target_Completion_Date | Actual_Completion_Date | Team_Size | Budget_Allocated | Budget_Spent | Resource_Utilization | Priorityy | Expected_Revenue_Impact | Actual_Revenue_Impact | Progress_Percentage | Assigned_Team | Display_Status
INIT0001 | Analytics Suite - Feature 1 | Analytics Suite | Testing | 2023-02-14 | 2023-06-23 |  | 8 | 1000000 | 617883 | 77 | Medium | 5000000 |  | 80% | Team Alpha | In Progress
INIT0002 | Mobile App - Feature 2 | Mobile App | On Hold | 2023-08-01 | 2023-10-08 |  | 12 | 100000 | 75327 | 66 | Low | 100000 |  | 25% | Team Alpha | In Progress
INIT0003 | Analytics Suite - Feature 3 | Analytics Suite | Planning | 2023-06-26 | 2023-11-08 |  | 10 | 250000 | 151608 | 96 | Medium | 5000000 |  | 10% | Team Epsilon | In Progress
INIT0004 | Mobile App - Feature 4 | Mobile App | In Development | 2023-03-15 | 2023-07-25 |  | 8 | 50000 | 30831 | 75 | Medium | 100000 |  | 50% | Team Delta | In Progress
INIT0005 | Data Infrastructure - Feature 5 | Data Infrastructure | Testing | 2023-06-22 | 2023-10-07 |  | 10 | 250000 | 131069 | 66 | Medium | 500000 |  | 80% | Team Alpha | In Progress
INIT0006 | Web Platform - Feature 6 | Web Platform | Testing | 2023-05-18 | 2023-10-01 |  | 6 | 1000000 | 816443 | 88 | Low | 500000 |  | 80% | Team Gamma | In Progress
INIT0007 | Data Infrastructure - Feature 7 | Data Infrastructure | Launched | 2023-09-21 | 2023-11-30 | 2023-12-03 | 11 | 500000 | 204259 | 96 | Medium | 100000 | 62161 | 100% | Team Alpha | Completed
INIT0008 | Web Platform - Feature 8 | Web Platform | Planning | 2023-08-22 | 2023-10-03 |  | 7 | 250000 | 215926 | 83 | High | 5000000 |  | 10% | Team Alpha | In Progress
INIT0009 | Analytics Suite - Feature 9 | Analytics Suite | Launched | 2023-05-04 | 2023-09-06 | 2023-09-08 | 10 | 100000 | 106841 | 97 | Critical | 1000000 | 740974 | 100% | Team Alpha | Completed
INIT0010 | API - Feature 10 | API | Planning | 2023-07-17 | 2023-08-28 |  | 15 | 100000 | 98305 | 73 | Medium | 500000 |  | 10% | Team Alpha | In Progress
INIT0011 | Web Platform - Feature 11 | Web Platform | In Development | 2023-09-20 | 2023-10-25 |  | 5 | 50000 | 33963 | 71 | Medium | 100000 |  | 50% | Team Delta | In Progress
INIT0012 | Web Platform - Feature 12 | Web Platform | Testing | 2023-08-05 | 2023-12-09 |  | 6 | 250000 | 166799 | 89 | Medium | 1000000 |  | 80% | Team Gamma | In Progress
INIT0013 | Analytics Suite - Feature 13 | Analytics Suite | On Hold | 2023-02-22 | 2023-03-25 |  | 8 | 1000000 | 1099543 | 95 | Low | 1000000 |  | 25% | Team Epsilon | In Progress
INIT0014 | API - Feature 14 | API | Planning | 2023-06-22 | 2023-09-30 |  | 7 | 250000 | 247298 | 79 | Low | 500000 |  | 10% | Team Alpha | In Progress
INIT0015 | Web Platform - Feature 15 | Web Platform | On Hold | 2023-11-04 | 2024-03-16 |  | 14 | 250000 | 211151 | 61 | High | 5000000 |  | 25% | Team Alpha | In Progress
INIT0016 | API - Feature 16 | API | Testing | 2023-07-18 | 2023-08-26 |  | 12 | 1000000 | 866455 | 72 | Low | 1000000 |  | 80% | Team Delta | In Progress
INIT0017 | Web Platform - Feature 17 | Web Platform | On Hold | 2023-09-17 | 2024-01-01 |  | 11 | 100000 | 97251 | 71 | Low | 1000000 |  | 25% | Team Gamma | In Progress
INIT0018 | Mobile App - Feature 18 | Mobile App | Launched | 2023-10-14 | 2023-12-29 | 2024-01-24 | 6 | 50000 | 23890 | 79 | High | 5000000 | 5258316 | 100% | Team Gamma | Completed
INIT0019 | API - Feature 19 | API | Testing | 2023-05-31 | 2023-10-26 |  | 13 | 50000 | 33821 | 97 | Medium | 100000 |  | 80% | Team Epsilon | In Progress
INIT0020 | Data Infrastructure - Feature 20 | Data Infrastructure | In Development | 2023-09-29 | 2024-01-13 |  | 5 | 500000 | 171624 | 68 | Critical | 500000 |  | 50% | Team Delta | In Progress
INIT0021 | API - Feature 21 | API | Launched | 2023-06-11 | 2023-08-26 | 2023-10-01 | 5 | 250000 | 201206 | 80 | Low | 100000 | 50329 | 100% | Team Beta | Completed
INIT0022 | API - Feature 22 | API | In Development | 2023-03-23 | 2023-08-25 |  | 9 | 50000 | 20176 | 100 | High | 5000000 |  | 50% | Team Epsilon | In Progress
INIT0023 | Data Infrastructure - Feature 23 | Data Infrastructure | Launched | 2023-01-03 | 2023-02-11 | 2023-02-11 | 15 | 50000 | 50680 | 93 | Low | 500000 | 256270 | 100% | Team Delta | Completed
INIT0024 | Mobile App - Feature 24 | Mobile App | In Development | 2023-06-09 | 2023-08-11 |  | 12 | 50000 | 30342 | 79 | High | 500000 |  | 50% | Team Gamma | In Progress
INIT0025 | Mobile App - Feature 25 | Mobile App | Planning | 2023-08-22 | 2024-02-01 |  | 9 | 1000000 | 719294 | 68 | Medium | 1000000 |  | 10% | Team Gamma | In Progress
INIT0026 | Data Infrastructure - Feature 26 | Data Infrastructure | Testing | 2023-07-26 | 2023-08-29 |  | 5 | 100000 | 47945 | 73 | High | 100000 |  | 80% | Team Beta | In Progress
INIT0027 | Analytics Suite - Feature 27 | Analytics Suite | On Hold | 2023-07-07 | 2023-08-15 |  | 7 | 500000 | 500617 | 94 | High | 100000 |  | 25% | Team Alpha | In Progress
INIT0028 | Analytics Suite - Feature 28 | Analytics Suite | Planning | 2023-01-25 | 2023-03-25 |  | 4 | 500000 | 327725 | 95 | Critical | 1000000 |  | 10% | Team Alpha | In Progress
INIT0029 | Data Infrastructure - Feature 29 | Data Infrastructure | In Development | 2023-06-04 | 2023-10-19 |  | 7 | 50000 | 41499 | 99 | High | 500000 |  | 50% | Team Alpha | In Progress
INIT0030 | Data Infrastructure - Feature 30 | Data Infrastructure | Planning | 2023-02-28 | 2023-04-26 |  | 6 | 500000 | 229458 | 76 | Critical | 500000 |  | 10% | Team Gamma | In Progress
INIT0031 | API - Feature 31 | API | Launched | 2023-01-21 | 2023-07-10 | 2023-07-08 | 3 | 500000 | 282241 | 60 | Medium | 100000 | 113481 | 100% | Team Beta | Completed
INIT0032 | Analytics Suite - Feature 32 | Analytics Suite | Launched | 2023-09-19 | 2023-11-07 | 2023-11-18 | 10 | 250000 | 203867 | 78 | High | 1000000 | 824994 | 100% | Team Alpha | Completed
INIT0033 | Mobile App - Feature 33 | Mobile App | In Development | 2023-07-04 | 2023-10-22 |  | 4 | 500000 | 445416 | 62 | Critical | 100000 |  | 50% | Team Gamma | In Progress
INIT0034 | Web Platform - Feature 34 | Web Platform | In Development | 2023-08-13 | 2023-11-19 |  | 8 | 50000 | 29904 | 71 | Medium | 100000 |  | 50% | Team Gamma | In Progress
INIT0035 | Data Infrastructure - Feature 35 | Data Infrastructure | Launched | 2023-07-17 | 2023-12-16 | 2024-01-31 | 14 | 100000 | 39044 | 63 | Low | 500000 | 286299 | 100% | Team Gamma | Completed
INIT0036 | Analytics Suite - Feature 36 | Analytics Suite | Launched | 2023-11-09 | 2024-03-15 | 2024-04-28 | 14 | 50000 | 49503 | 68 | Low | 5000000 | 5721392 | 100% | Team Beta | Completed
INIT0037 | Mobile App - Feature 37 | Mobile App | Launched | 2023-02-02 | 2023-05-09 | 2023-05-04 | 12 | 1000000 | 914022 | 96 | Low | 500000 | 592263 | 100% | Team Alpha | Completed
INIT0038 | API - Feature 38 | API | On Hold | 2023-12-05 | 2024-03-07 |  | 13 | 500000 | 288299 | 84 | Critical | 500000 |  | 25% | Team Delta | In Progress
INIT0039 | Analytics Suite - Feature 39 | Analytics Suite | On Hold | 2023-11-26 | 2024-02-04 |  | 10 | 1000000 | 979076 | 70 | Critical | 100000 |  | 25% | Team Alpha | In Progress
INIT0040 | Data Infrastructure - Feature 40 | Data Infrastructure | Testing | 2023-05-23 | 2023-07-04 |  | 13 | 1000000 | 478165 | 84 | High | 5000000 |  | 80% | Team Gamma | In Progress
INIT0041 | Web Platform - Feature 41 | Web Platform | Planning | 2023-10-21 | 2024-03-13 |  | 10 | 50000 | 49263 | 80 | Low | 100000 |  | 10% | Team Delta | In Progress
INIT0042 | Data Infrastructure - Feature 42 | Data Infrastructure | Planning | 2023-07-31 | 2023-09-08 |  | 4 | 1000000 | 739279 | 98 | Critical | 1000000 |  | 10% | Team Delta | In Progress
INIT0043 | Analytics Suite - Feature 43 | Analytics Suite | On Hold | 2023-06-24 | 2023-10-25 |  | 10 | 50000 | 47663 | 81 | High | 5000000 |  | 25% | Team Delta | In Progress
INIT0044 | API - Feature 44 | API | Launched | 2023-12-04 | 2024-02-28 | 2024-02-28 | 8 | 250000 | 184538 | 66 | Critical | 100000 | 112781 | 100% | Team Alpha | Completed
INIT0045 | Data Infrastructure - Feature 45 | Data Infrastructure | In Development | 2023-05-11 | 2023-07-30 |  | 9 | 100000 | 39659 | 73 | Low | 5000000 |  | 50% | Team Alpha | In Progress
INIT0046 | Web Platform - Feature 46 | Web Platform | Testing | 2023-01-24 | 2023-07-23 |  | 10 | 50000 | 45885 | 89 | Critical | 500000 |  | 80% | Team Delta | In Progress
INIT0047 | Data Infrastructure - Feature 47 | Data Infrastructure | Planning | 2023-08-10 | 2024-02-05 |  | 15 | 500000 | 519748 | 71 | Critical | 500000 |  | 10% | Team Epsilon | In Progress
INIT0048 | Web Platform - Feature 48 | Web Platform | Planning | 2023-11-07 | 2024-02-27 |  | 9 | 1000000 | 1005112 | 98 | Low | 500000 |  | 10% | Team Epsilon | In Progress
INIT0049 | API - Feature 49 | API | Launched | 2023-08-20 | 2023-10-23 | 2023-10-27 | 14 | 1000000 | 539130 | 95 | Medium | 1000000 | 998312 | 100% | Team Gamma | Completed
INIT0050 | Analytics Suite - Feature 50 | Analytics Suite | In Development | 2023-11-16 | 2024-02-28 |  | 5 | 250000 | 259238 | 71 | High | 1000000 |  | 50% | Team Beta | In Progress
INIT0051 | Mobile App - Feature 51 | Mobile App | Testing | 2023-10-20 | 2024-03-04 |  | 9 | 1000000 | 528742 | 60 | Low | 100000 |  | 80% | Team Epsilon | In Progress
INIT0052 | Mobile App - Feature 52 | Mobile App | Launched | 2023-12-10 | 2024-01-23 | 2024-01-20 | 5 | 250000 | 211678 | 63 | High | 1000000 | 642800 | 100% | Team Alpha | Completed
INIT0053 | Analytics Suite - Feature 53 | Analytics Suite | Planning | 2023-02-22 | 2023-08-14 |  | 11 | 100000 | 89393 | 84 | Medium | 500000 |  | 10% | Team Delta | In Progress
INIT0054 | Analytics Suite - Feature 54 | Analytics Suite | Testing | 2023-07-18 | 2023-12-01 |  | 3 | 250000 | 268166 | 60 | Critical | 1000000 |  | 80% | Team Delta | In Progress
INIT0055 | Web Platform - Feature 55 | Web Platform | On Hold | 2023-11-21 | 2024-03-24 |  | 12 | 1000000 | 737292 | 72 | Low | 500000 |  | 25% | Team Beta | In Progress
INIT0056 | API - Feature 56 | API | Launched | 2023-04-06 | 2023-06-19 | 2023-07-01 | 7 | 500000 | 166253 | 95 | High | 1000000 | 591046 | 100% | Team Alpha | Completed
INIT0057 | Analytics Suite - Feature 57 | Analytics Suite | Testing | 2023-08-27 | 2023-11-04 |  | 8 | 50000 | 21148 | 98 | Critical | 100000 |  | 80% | Team Gamma | In Progress
INIT0058 | Analytics Suite - Feature 58 | Analytics Suite | Testing | 2023-10-09 | 2024-02-07 |  | 8 | 50000 | 46361 | 93 | Low | 500000 |  | 80% | Team Epsilon | In Progress
INIT0059 | Web Platform - Feature 59 | Web Platform | On Hold | 2023-03-23 | 2023-08-06 |  | 4 | 1000000 | 729628 | 82 | Critical | 500000 |  | 25% | Team Epsilon | In Progress
INIT0060 | Web Platform - Feature 60 | Web Platform | Testing | 2023-05-31 | 2023-08-24 |  | 11 | 1000000 | 724399 | 60 | Medium | 100000 |  | 80% | Team Gamma | In Progress
INIT0061 | API - Feature 61 | API | Launched | 2023-11-15 | 2024-02-15 | 2024-04-03 | 15 | 250000 | 151274 | 67 | High | 5000000 | 3398066 | 100% | Team Epsilon | Completed
INIT0062 | API - Feature 62 | API | Planning | 2023-09-18 | 2024-02-09 |  | 13 | 500000 | 167540 | 72 | Medium | 1000000 |  | 10% | Team Epsilon | In Progress
INIT0063 | Analytics Suite - Feature 63 | Analytics Suite | Planning | 2023-10-03 | 2024-03-17 |  | 6 | 50000 | 40077 | 100 | Critical | 500000 |  | 10% | Team Beta | In Progress
INIT0064 | Data Infrastructure - Feature 64 | Data Infrastructure | Planning | 2023-12-26 | 2024-05-15 |  | 5 | 50000 | 44875 | 61 | High | 5000000 |  | 10% | Team Epsilon | In Progress
INIT0065 | API - Feature 65 | API | Planning | 2023-01-28 | 2023-04-13 |  | 12 | 250000 | 186616 | 74 | Critical | 1000000 |  | 10% | Team Alpha | In Progress
INIT0066 | Data Infrastructure - Feature 66 | Data Infrastructure | Launched | 2023-08-10 | 2023-11-28 | 2023-12-03 | 13 | 50000 | 36393 | 99 | Low | 100000 | 102917 | 100% | Team Delta | Completed
INIT0067 | Analytics Suite - Feature 67 | Analytics Suite | Planning | 2023-09-15 | 2023-11-11 |  | 7 | 250000 | 232378 | 98 | Critical | 100000 |  | 10% | Team Gamma | In Progress
INIT0068 | API - Feature 68 | API | Launched | 2023-12-05 | 2024-01-11 | 2024-01-14 | 9 | 100000 | 40910 | 94 | Low | 1000000 | 1172093 | 100% | Team Delta | Completed
INIT0069 | Web Platform - Feature 69 | Web Platform | Testing | 2023-10-11 | 2024-03-31 |  | 3 | 100000 | 39858 | 96 | Medium | 5000000 |  | 80% | Team Alpha | In Progress
INIT0070 | Analytics Suite - Feature 70 | Analytics Suite | On Hold | 2023-04-18 | 2023-08-14 |  | 13 | 100000 | 63012 | 92 | Critical | 500000 |  | 25% | Team Gamma | In Progress
INIT0071 | Web Platform - Feature 71 | Web Platform | In Development | 2023-05-10 | 2023-07-28 |  | 15 | 50000 | 22254 | 96 | High | 100000 |  | 50% | Team Epsilon | In Progress
INIT0072 | Analytics Suite - Feature 72 | Analytics Suite | Launched | 2023-12-10 | 2024-01-26 | 2024-01-24 | 8 | 1000000 | 689752 | 82 | Critical | 500000 | 484953 | 100% | Team Gamma | Completed
INIT0073 | Web Platform - Feature 73 | Web Platform | Planning | 2023-02-05 | 2023-04-25 |  | 8 | 250000 | 172172 | 99 | Medium | 1000000 |  | 10% | Team Epsilon | In Progress
INIT0074 | Analytics Suite - Feature 74 | Analytics Suite | In Development | 2023-08-08 | 2023-10-20 |  | 15 | 50000 | 27528 | 74 | Medium | 5000000 |  | 50% | Team Gamma | In Progress
INIT0075 | API - Feature 75 | API | Testing | 2023-09-03 | 2024-01-29 |  | 7 | 500000 | 293496 | 91 | High | 100000 |  | 80% | Team Gamma | In Progress
INIT0076 | Web Platform - Feature 76 | Web Platform | On Hold | 2023-03-13 | 2023-08-27 |  | 13 | 100000 | 51058 | 64 | Critical | 100000 |  | 25% | Team Gamma | In Progress
INIT0077 | Mobile App - Feature 77 | Mobile App | On Hold | 2023-10-24 | 2024-03-05 |  | 3 | 1000000 | 470208 | 95 | Critical | 1000000 |  | 25% | Team Epsilon | In Progress
INIT0078 | Analytics Suite - Feature 78 | Analytics Suite | On Hold | 2023-07-07 | 2023-11-14 |  | 12 | 100000 | 101315 | 78 | Low | 500000 |  | 25% | Team Beta | In Progress
INIT0079 | Data Infrastructure - Feature 79 | Data Infrastructure | On Hold | 2023-07-06 | 2023-12-11 |  | 15 | 50000 | 41507 | 99 | Critical | 500000 |  | 25% | Team Delta | In Progress
INIT0080 | Analytics Suite - Feature 80 | Analytics Suite | In Development | 2023-04-02 | 2023-09-23 |  | 5 | 1000000 | 827530 | 90 | Low | 1000000 |  | 50% | Team Beta | In Progress
In Progress
In Progress
In Progress
In Progress

## Pivots
Pivot – Budget Performance by Product Line
Product Line | Budget Allocated | Budget Spent | Sum of Variance
Analytics Suite | 7950000 | 6750224 | 1199776
API | 6050000 | 3767558 | 2282442
Data Infrastructure | 4800000 | 2815204 | 1984796
Mobile App | 5000000 | 3449750 | 1550250
Web Platform | 6550000 | 5148358 | 1401642
(blank) |  |  | 0
Grand Total | 30350000 | 21931094 | 8418906
Revenue Impact (Expected vs Actual)
Pivot – Average Progress by Status |  |  |  |  | Initiative Name | Expected Revenue (£) | Actual Revenue (£) | Count of Initiative_Name | Column Labels
Product_Line | (All) |  |  |  | Analytics Suite - Feature 1 | 5000000 |  | Product Line | Completed | In Progress | Grand Total
[5 empty] | Analytics Suite - Feature 13 | 1000000 |  | Analytics Suite | 4 | 18 | 22
Display Status | Sum of Progress_True (%) |  |  |  | Analytics Suite - Feature 27 | 100000 |  | API | 7 | 9 | 16
In Progress | 24.85% |  |  |  | Analytics Suite - Feature 28 | 1000000 |  | Data Infrastructure | 4 | 11 | 15
Completed | 18% |  |  |  | Analytics Suite - Feature 3 | 5000000 |  | Mobile App | 3 | 7 | 10
Grand Total | 42.85% |  |  |  | Analytics Suite - Feature 32 | 1000000 | 824994 | Web Platform |  | 17 | 17
[5 empty] | Analytics Suite - Feature 36 | 5000000 | 5721392 | (blank)
Pivot – Team Size & Average Utilization by Team |  |  |  |  | Analytics Suite - Feature 39 | 100000
Team | Team Size | Avg Resource Utilization (%) |  |  | Analytics Suite - Feature 43 | 5000000
Team Alpha | 188 | 80.8095 |  |  | Analytics Suite - Feature 50 | 1000000
Team Beta | 67 | 76.8889 |  |  | Analytics Suite - Feature 53 | 500000
Team Delta | 143 | 83.1333 |  |  | Analytics Suite - Feature 54 | 1000000
Team Epsilon | 144 | 85.4667 |  |  | Analytics Suite - Feature 57 | 100000
Team Gamma | 191 | 79.2 |  |  | Analytics Suite - Feature 58 | 500000
(blank) |  |  |  |  | Analytics Suite - Feature 63 | 500000
Grand Total | 733 | 81.275 |  |  | Analytics Suite - Feature 67 | 100000
[5 empty] | Analytics Suite - Feature 70 | 500000
Pivot - Schedule Overview (Target Vs Actual) |  |  |  |  | Analytics Suite - Feature 72 | 500000 | 484953
| Display_Status | Values |  |  | Analytics Suite - Feature 74 | 5000000
| Completed | Completed | In Progress | In Progress | Analytics Suite - Feature 78 | 500000
Initiative | Target Date | Actual Date | Target Date | Actual Date | Analytics Suite - Feature 80 | 1000000
Analytics Suite - Feature 1 |  |  | 2023-06-23 |  | Analytics Suite - Feature 9 | 1000000 | 740974
Analytics Suite - Feature 13 |  |  | 2023-03-25 |  | API - Feature 10 | 500000
Analytics Suite - Feature 27 |  |  | 2023-08-15 |  | API - Feature 14 | 500000
Analytics Suite - Feature 28 |  |  | 2023-03-25 |  | API - Feature 16 | 1000000
Analytics Suite - Feature 3 |  |  | 2023-11-08 |  | API - Feature 19 | 100000
Analytics Suite - Feature 32 | 2023-11-07 | 2023-11-18 |  |  | API - Feature 21 | 100000 | 50329
Analytics Suite - Feature 36 | 2024-03-15 | 2024-04-28 |  |  | API - Feature 22 | 5000000
Analytics Suite - Feature 39 |  |  | 2024-02-04 |  | API - Feature 31 | 100000 | 113481
Analytics Suite - Feature 43 |  |  | 2023-10-25 |  | API - Feature 38 | 500000
Analytics Suite - Feature 50 |  |  | 2024-02-28 |  | API - Feature 44 | 100000 | 112781
Analytics Suite - Feature 53 |  |  | 2023-08-14 |  | API - Feature 49 | 1000000 | 998312
Analytics Suite - Feature 54 |  |  | 2023-12-01 |  | API - Feature 56 | 1000000 | 591046
Analytics Suite - Feature 57 |  |  | 2023-11-04 |  | API - Feature 61 | 5000000 | 3398066
Analytics Suite - Feature 58 |  |  | 2024-02-07 |  | API - Feature 62 | 1000000
Analytics Suite - Feature 63 |  |  | 2024-03-17 |  | API - Feature 65 | 1000000
Analytics Suite - Feature 67 |  |  | 2023-11-11 |  | API - Feature 68 | 1000000 | 1172093
Analytics Suite - Feature 70 |  |  | 2023-08-14 |  | API - Feature 75 | 100000
Analytics Suite - Feature 72 | 2024-01-26 | 2024-01-24 |  |  | Data Infrastructure - Feature 20 | 500000
Analytics Suite - Feature 74 |  |  | 2023-10-20 |  | Data Infrastructure - Feature 23 | 500000 | 256270
Analytics Suite - Feature 78 |  |  | 2023-11-14 |  | Data Infrastructure - Feature 26 | 100000
Analytics Suite - Feature 80 |  |  | 2023-09-23 |  | Data Infrastructure - Feature 29 | 500000
Analytics Suite - Feature 9 | 2023-09-06 | 2023-09-08 |  |  | Data Infrastructure - Feature 30 | 500000
API - Feature 10 |  |  | 2023-08-28 |  | Data Infrastructure - Feature 35 | 500000 | 286299
API - Feature 14 |  |  | 2023-09-30 |  | Data Infrastructure - Feature 40 | 5000000
API - Feature 16 |  |  | 2023-08-26 |  | Data Infrastructure - Feature 42 | 1000000
API - Feature 19 |  |  | 2023-10-26 |  | Data Infrastructure - Feature 45 | 5000000
API - Feature 21 | 2023-08-26 | 2023-10-01 |  |  | Data Infrastructure - Feature 47 | 500000
API - Feature 22 |  |  | 2023-08-25 |  | Data Infrastructure - Feature 5 | 500000
API - Feature 31 | 2023-07-10 | 2023-07-08 |  |  | Data Infrastructure - Feature 64 | 5000000
API - Feature 38 |  |  | 2024-03-07 |  | Data Infrastructure - Feature 66 | 100000 | 102917
API - Feature 44 | 2024-02-28 | 2024-02-28 |  |  | Data Infrastructure - Feature 7 | 100000 | 62161
API - Feature 49 | 2023-10-23 | 2023-10-27 |  |  | Data Infrastructure - Feature 79 | 500000
API - Feature 56 | 2023-06-19 | 2023-07-01 |  |  | Mobile App - Feature 18 | 5000000 | 5258316
API - Feature 61 | 2024-02-15 | 2024-04-03 |  |  | Mobile App - Feature 2 | 100000
API - Feature 62 |  |  | 2024-02-09 |  | Mobile App - Feature 24 | 500000
API - Feature 65 |  |  | 2023-04-13 |  | Mobile App - Feature 25 | 1000000
API - Feature 68 | 2024-01-11 | 2024-01-14 |  |  | Mobile App - Feature 33 | 100000
API - Feature 75 |  |  | 2024-01-29 |  | Mobile App - Feature 37 | 500000 | 592263
Data Infrastructure - Feature 20 |  |  | 2024-01-13 |  | Mobile App - Feature 4 | 100000
Data Infrastructure - Feature 23 | 2023-02-11 | 2023-02-11 |  |  | Mobile App - Feature 51 | 100000
Data Infrastructure - Feature 26 |  |  | 2023-08-29 |  | Mobile App - Feature 52 | 1000000 | 642800
Data Infrastructure - Feature 29 |  |  | 2023-10-19 |  | Mobile App - Feature 77 | 1000000
Data Infrastructure - Feature 30 |  |  | 2023-04-26 |  | Web Platform - Feature 11 | 100000
Data Infrastructure - Feature 35 | 2023-12-16 | 2024-01-31 |  |  | Web Platform - Feature 12 | 1000000
Data Infrastructure - Feature 40 |  |  | 2023-07-04 |  | Web Platform - Feature 15 | 5000000
Data Infrastructure - Feature 42 |  |  | 2023-09-08 |  | Web Platform - Feature 17 | 1000000
Data Infrastructure - Feature 45 |  |  | 2023-07-30 |  | Web Platform - Feature 34 | 100000
Data Infrastructure - Feature 47 |  |  | 2024-02-05 |  | Web Platform - Feature 41 | 100000
Data Infrastructure - Feature 5 |  |  | 2023-10-07 |  | Web Platform - Feature 46 | 500000
Data Infrastructure - Feature 64 |  |  | 2024-05-15 |  | Web Platform - Feature 48 | 500000
Data Infrastructure - Feature 66 | 2023-11-28 | 2023-12-03 |  |  | Web Platform - Feature 55 | 500000
Data Infrastructure - Feature 7 | 2023-11-30 | 2023-12-03 |  |  | Web Platform - Feature 59 | 500000
Data Infrastructure - Feature 79 |  |  | 2023-12-11 |  | Web Platform - Feature 6 | 500000
Mobile App - Feature 18 | 2023-12-29 | 2024-01-24 |  |  | Web Platform - Feature 60 | 100000
Mobile App - Feature 2 |  |  | 2023-10-08 |  | Web Platform - Feature 69 | 5000000
Mobile App - Feature 24 |  |  | 2023-08-11 |  | Web Platform - Feature 71 | 100000
Mobile App - Feature 25 |  |  | 2024-02-01 |  | Web Platform - Feature 73 | 1000000
Mobile App - Feature 33 |  |  | 2023-10-22 |  | Web Platform - Feature 76 | 100000
Mobile App - Feature 37 | 2023-05-09 | 2023-05-04 |  |  | Web Platform - Feature 8 | 5000000
Mobile App - Feature 4 |  |  | 2023-07-25 |  | (blank)
Mobile App - Feature 51 |  |  | 2024-03-04 |  | Grand Total | 104200000 | 21409447
Mobile App - Feature 52 | 2024-01-23 | 2024-01-20
Mobile App - Feature 77 |  |  | 2024-03-05
Web Platform - Feature 11 |  |  | 2023-10-25
Web Platform - Feature 12 |  |  | 2023-12-09
Web Platform - Feature 15 |  |  | 2024-03-16
Web Platform - Feature 17 |  |  | 2024-01-01
Web Platform - Feature 34 |  |  | 2023-11-19
Web Platform - Feature 41 |  |  | 2024-03-13
Web Platform - Feature 46 |  |  | 2023-07-23
Web Platform - Feature 48 |  |  | 2024-02-27
Web Platform - Feature 55 |  |  | 2024-03-24
Web Platform - Feature 59 |  |  | 2023-08-06
Web Platform - Feature 6 |  |  | 2023-10-01
Web Platform - Feature 60 |  |  | 2023-08-24
Web Platform - Feature 69 |  |  | 2024-03-31
Web Platform - Feature 71 |  |  | 2023-07-28
Web Platform - Feature 73 |  |  | 2023-04-25
Web Platform - Feature 76 |  |  | 2023-08-27
Web Platform - Feature 8 |  |  | 2023-10-03

## Dashboard
Initiative Performance Dashboard – October 2025
| Budget Performance by Product Line | Progress by Status (%) |  | KPI | Output
|  |  |  | Total Initiatives | 12
|  |  |  | % Completed | 65%
|  |  |  | Budget Utilization | 78%
|  |  |  | Avg Resource Utilization | 84%
Revenue Impact (Expected vs Actual)
Team Utilization Overview
Initiatives by Product Line & Status
Initiative Timeline (Target vs Actual
Prepared by Lewis T – October 2025
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Executive Summary
• A total of 12 initiatives are being tracked, with 65% completed to date.
• Budget utilisation stands at 78%, indicating strong financial performance.
• Average resource utilisation is 84%, showing balanced team workloads.
• Revenue impact remains positive, with most initiatives achieving targets.
• The project timeline indicates the majority of initiatives are on track, with minor delays noted in select areas.
• Overall status: On Track

## Notes
Key Insights:
• Overall progress: 65% completed
• Budget variance: £X under budget
• Teams: 3 of 5 fully utilized