## schedule
Week | Sarah Mitchell | David Chen | Maria Rodriguez | James Thompson | Emily Watson | Robert Johnson | Lisa Anderson | District Out | The schedule was built to meet all initial conditions and constraints while ensuring fairness and proper coverage: 1. District Coverage: All three high-traffic districts (Downtown, Mall Area, Airport Zone) are inspected each week. Three residential districts are inspected weekly, leaving one residential district out. 2. Auditor Workload: Each auditor completes 3 high-traffic and 3 residential inspections during the season, with no district repeated. 3. Training/Vacation: One auditor is on training or vacation each week, and they are not assigned inspections during that time. 4. Weekly Rules: Each auditor performs only one inspection per week, and each district is inspected by only one auditor per week.
1 | West Residential | East Residential | Downtown | Airport Zone | South Residential | (T/V) | Mall Area | North Residential
2 | (T/V) | South Residential | North Residential | West Residential | Downtown | Mall Area | Airport Zone | East Residential
3 | Mall Area | Downtown | West Residential | North Residential | Airport Zone | South Residential | (T/V) | East Residential
4 | East Residential | West Residential | (T/V) | Downtown | Mall Area | Airport Zone | South Residential | North Residential
5 | Airport Zone | Mall Area | East Residential | South Residential | (T/V) | Downtown | North Residential | West Residential
6 | Downtown | Airport Zone | Mall Area | (T/V) | West Residential | North Residential | East Residential | South Residential
7 | South Residential | (T/V) | Airport Zone | Mall Area | North Residential | East Residential | Downtown | West Residential