# AI Transformation Roadmap for LIS Digital — From Digital Marketing to AI-Powered Communications Agency

Executive Summary:

LIS Digital will reposition from a traditional international communications agency into an AI-first digital communications & marketing firm that keeps legacy PR and communications capabilities but offers AI-powered services as the primary value proposition.

Goal: deliver faster, higher-margin, scalable services (media monitoring, automated content, predictive campaign analytics, chatbots) for tech, finance, and healthcare clients.

Budget available: €35,000 (year 1) for tech, training, and pilots.

Objectives:

- Rebrand & reposition LIS Digital as an AI-driven communications firm.

- Build 4 core AI services and productize them.

- Run 2–3 pilot projects in the first 3 months and convert them into paid retainer clients.

- Train internal teams to run AI pipelines with low/no-code where possible; reserve custom dev for flagship clients.

- Deliver a step-by-step implementation plan, tech recommendations, training pathway, pricing, and marketing repositioning plan.

Scope:

- A detailed transformation roadmap (phased plan).

- Tech & software stack (low/no-code priority + custom options).

- Training pathway & role-based curricula.

- Example workflows for four services (step-by-step).

- Sample pricing packages and pilot offers.

- Budget allocation for the €35k first-year cap.

- KPIs, reporting templates, risk & compliance checklist.

- Client pilot brief & onboarding checklist.

Phase Overview:

- Phase 0 — Audit & Baseline (Week 0–1): collect data, map capabilities & clients.

- Phase 1 — Positioning & Productization (Week 2): define services, packaging & legal.

- Phase 2 — Tech Setup (Week 3–5): choose core tools, set up accounts, build templates.

- Phase 3 — Training & Internal Pilots (Week 6–10): train team, run internal demos.

- Phase 4 — External Pilot Clients (Week 11–16): run 2–3 client pilots, measure results.

- Phase 5 — Scale & Go-to-Market (Week 17–24): website, sales, PR, convert pilots to retainers.

Phase 0 — Audit & Baseline (Week 0–1):

- Collect essentials (Day 1–Collect essentials):

- Export the last 12 months' revenue by client and service (CSV).

- List 20 top clients (by revenue, industry: tech/finance/healthcare).

- Inventory staff skills (10–30 staff): who does PR, who does content, who does dev? Create a skills matrix.

- Quick profitability scan (Do this day 2–3):

- For each main service, estimate hours per month and margin (hourly cost × hours).

- Flag repetitive, manual tasks suitable for automation (content drafting, reporting, monitoring).

- Client fit matrix (Do this day 4):

- For each top client, score 1–5 for AI readiness and strategic importance. Prioritize 3 pilot candidates.

- Deliverable → “Agency Baseline PDF”:

- Capability Map

- Top 5 Quick-Win AI Use Cases

Phase 1 — Positioning & Productization (Week 2):

- Draft & finalize positioning statement:

- Draft a clear and compelling statement that communicates LIS Digital’s AI-powered value proposition.

- Review internally and finalize approval for use in marketing materials, proposals, and the website.

- Productize 4 core services (create 1-pager for each):

- AI Media Intelligence & Sentiment — real-time tracking, automated alerts, weekly insight reports.

- Automated Content Factory — press releases, blogs, localized social posts (AI draft + editor).

- Predictive Campaign Analytics — campaign forecasts, actionable optimizations, and spend allocation suggestions.

- Conversational AI & Chatbots — lead qualification, FAQ, crisis routing.

For each 1-pager, include: scope, deliverables, sample timeline, price range, and KPIs.

- Legal & policy update:

- Update T&Cs & data usage clauses to include AI, client opt-ins for data usage, and IP terms.

- Deliverable:

- 4 product one-pagers + updated T&Cs draft.

Phase 2 — Tech Stack & Implementation (Week 3–5) — Concrete setup:

Principle: prefer low/no-code options that enable rapid pilots. Use managed LLMs (Large Language Model) & managed vector DB to minimize engineering overhead.

- Core stack (recommended, low-code first):

- LLM / AI inference: OpenAI (GPT-4x/GPT-4o) or Anthropic Claude (pick one primary).

- Prompt orchestration / RAG: LlamaIndex or LangChain (hosted workflows) — use low-code wrappers (Hugging Face + hosted LangChain).

- Vector DB: Pinecone (managed) or Weaviate (managed).

- Automation / Integrations: Zapier / Make (Integromat) / n8n for workflows.

- Media Monitoring: Meltwater or Brandwatch (paid) OR set up custom ingest using RSS + social APIs + LLM for sentiment if budget is tight.

- Chatbot integration: Intercom / Drift / ManyChat or custom bot using Botpress + OpenAI.

- Content generation & QA: OpenAI + internal editor + Grammarly / Writer for brand voice.

- Image/Video generation: Midjourney / Stable Diffusion / Runway for short videos.

- BI & dashboards: GA4 + Looker Studio or Metabase for internal dashboards.

- Project ops & docs: Notion (runbooks), Slack, HubSpot or Pipedrive for sales.

- Concrete setup tasks:

- Create org accounts for OpenAI (or Anthropic), Pinecone, Zapier, Notion, and a media monitoring tool trial.

- Build a shared prompt library in Notion with initial templates (press release, blog outline, ad copy, sentiment summary).

- Create a pilot ingestion flow: social + news RSS → daily fetch → vectorize → run sentiment summarization prompt → deliver daily digest to Slack/email.

- Deliverable:

- Working pilot environment (credentials document + 1 Notion prompt library + one automated media digest).

Phase 3 — Training & Internal Pilots (Week 6–10):

Objective: upskill staff (PR/content/analytics) and validate workflows internally.

Training program (8 weeks condensed into 5 weeks of intensive training)

- Week A (2 days) — LLM basics & safety:

- Intro to LLMs, hallucinations, temperature, and token costs.

- Workshop: generate a press release draft from a short brief.

- Week B (3 days) — Prompt engineering & templates:

- Build prompts for: media summary, sentiment bullets, blog outline, ad variants.

- Create templates & QA checklist.

- Week C (3 days) — Integrations & RAG basics:

- Hands-on: set up the Pinecone index from a sample client dataset.

- Build a small retrieval bot that answers FAQs from client docs.

- Week D (5 days) — Workflows & SOPs:

- Map 3 workflows: content pipeline, media monitoring, chatbot handover.

- Create runbooks in Notion for each workflow.

- Week E (3 days) — Mock client pilots & QA:

- Run 2 internal mock pilots end-to-end. Collect metrics & refine prompts.

- Roles & Owners:  assign clear owners for each AI product (product lead, prompt engineer, editor, analyst).

- Deliverable: Training completion report + 3 internal demo artifacts.

Phase 4 — External Client Pilots (Week 11–16) — How to run pilots:

- Pilot selection: choose 2–3 clients (from Phase 0 prioritized list); ideally, one from tech, one from healthcare/finance.

- Pilot design template (use with client):

- Objective: state measurable KPI (e.g., reduce PR response time, generate 8 SEO articles, decrease CPA by 20%).

- Scope: 4–6 week pilot; deliverables & acceptance criteria.

- Data & access needed: login to CMS, existing content, social accounts, media list, CRM access.

- Timeline & governance: weekly demos, Slack channel for the project.

- Cost: discounted pilot fee (see pricing section).

- Execution steps (for each pilot):

- Kickoff (Day 0–2): gather assets, define baseline metrics.

- Week 1: ingest client docs & media sources; build embeddings; set up monitoring.

- Week 2: produce first content batch (press release / 2 blog drafts) and weekly media digest.

- Week 3: deploy chatbot prototype (FAQ & lead capture) and run initial ad creative test.

- Week 4–6: iterate on prompts, tune RAG retrieval, run predictive analytics on ad data.

- Final week: present pilot results: KPIs vs baseline, recommended next steps + pricing for ongoing work.

- Deliverable: Pilot report & conversion proposal.

Phase 5 — Scale & Go-to-Market  (Week 17–24) — Marketing & Sales Playbook:

- Messaging & position (website copy + one-liner):

- One liner: LIS Digital — AI-powered communications that scale insight, content, and conversions.

- Top lines on site: AI Media Intelligence | Automated Content Factory | Predictive Campaigns | Conversational AI

- Website changes (practical checklist):

- Update hero & service pages with AI focus (copy & visuals).

- Add product one-pagers and transparent price ranges.

- Publish 3 quick case studies from pilots.

- Add lead form: “Request a free 2-week AI pilot” (linked to HubSpot/Pipedrive).

- Sales collateral:

- 1-page PDF for each service.

- ROI calculator (Google Sheet) for prospects (variables: baseline traffic/leads, expected lift %, lifetime value).

- Outreach plan (30/60/90 days):

- 30 days: reach out to top 30 existing clients, offer discounted pilots.

- 60 days: LinkedIn ad + lead gen for “AI pilot” offer, targeted to tech & finance CMOs.

- 90 days: PR/press release announcing agency relaunch, co-marketing with tool partners.

- Deliverable: Sales deck + 3 email templates + LinkedIn outreach sequence.

Pricing & Packaging

All prices in EUR

- Pilot Offers (introductory):

- 2-week AI Content Pilot: €750 — 2 optimized press releases + 4 social posts + performance summary.

- Ad Creative Sprint (2 weeks): €1,250 — 10 creatives + 1 scaled test.

- AI Monitoring Pilot: €1,000 — 4 weeks monitoring + weekly sentiment reports.

- Retainers (monthly productized):

- Retainers (monthly productized)

- 4 blog posts (AI draft + human edit), 8 social posts, basic media monitoring (weekly digest).

- Growth — €4,000/mo

- 8 blog posts, 20 social posts, 10 ad creatives/month, weekly performance report, basic chatbot (lead qualifier).

- Enterprise — €10,000+/mo

- Custom LLM integration, fine-tuned retrieval, full campaign forecasting, dedicated success manager, and SLA.

- One-time projects

- Custom LLM / Integration — €15k–€60k (scope dependent).

Pricing rationale: value-based; starter aimed to be accessible to convert existing clients; growth & enterprise reflect complexity.

Year-1 Budget Allocation (use the €35,000 cap) — concrete split

Total = €35,000

- Tooling & Licenses (managed services) — €8,000

- OpenAI / Anthropic usage, Pinecone, Zapier/Make monthly fees, media monitoring trial(s).

- Training & Staff Time — €7,000

- External courses, workshops, paid time for staff training & build sprints.

- Pilot Projects (discounted client work/delivery cost) — €10,000

- Paid hours to deliver 3 pilots: content production, ads budget (small test spends), and dev hours for integrations.

- Custom Development & Integrations — €7,000

- One small custom integration (chatbot + CRM push) or RAG pipeline for a pilot.

- Contingency / Marketing (website updates, PR) — €3,000

Arithmetic check: 8000 + 7000 = 15000; +10000 = 25000; +7000 = 32000; +3000 = 35000 → €35,000.

KPIs & Reporting (what to measure)

- Business KPIs: New MRR from AI services, conversion rate from pilots to retainers, average deal size, and client retention.

- Service KPIs by product:

- Media Intelligence: #alerts, sentiment delta, time to detect crisis.

- Content Factory: #articles/month, content production time, and organic traffic change.

- Predictive Analytics: forecast accuracy (MAPE), ROI uplift.

- Chatbots: qualified leads/day, handover rate to humans, conversion rate.

- Operational KPIs: Time-to-deliver per request, token cost per client, prompt reuse rate.

Reporting cadence: Weekly internal dashboard, monthly client report, quarterly business review.

Risk, Compliance & Quality

- Data privacy & client consent: add explicit opt-in for client data usage; sign Data Processing Agreement if storing PII.

- Hallucinations & brand safety: always human-in-the-loop for outbound content; QA checklist required.

- Cost overruns: set usage budgets & alerts on model spend.

- Intellectual property: define who owns prompts, generated content, and fine-tuned models in the contract.

Playbooks, Templates & Prompts

Objective: Provide ready-to-use operational tools so the agency can deliver AI services consistently and efficiently.

Included Materials:

- Prompt Library (Starter Set):

- Press Release Draft (short brief → full release)

- Blog Outline Generator (keyword/topic → 5-section outline)

- Sentiment Summary (media mentions → sentiment breakdown + key quotes)

- Ad Copy Variants (product description → 5 alternative ad creatives)

- Operational Playbooks:

- Content Workflow SOP: from client brief → AI draft → human edit → publish

- Media Monitoring SOP: setup → data ingestion → daily sentiment → reporting

- Chatbot Handover SOP: AI response flow → trigger points → handover to human agent

- Templates:

- KPI Dashboard Template (Google Looker Studio / Excel)

- Pilot Brief Template (scope, deliverables, success metrics)

- Reporting Template (weekly digest, monthly client report)

Deliverable: Packaged “AI Playbook Starter Kit” (Notion or PDF).

ROI Calculator — variables & sample formula

Inputs: baseline monthly leads (L0), baseline conversion rate (CR0), average deal value (ADV), expected lead lift % (ΔL), expected conversion lift % (ΔCR), and margin % on deals.

Simple projection:

- New leads = L0 × (1 + ΔL)

- New conversions = New leads × (CR0 × (1 + ΔCR))

- New revenue = New conversions × ADV

- Incremental revenue = New revenue − (L0 × CR0 × ADV)

- Payback months = Implementation cost / (monthly incremental gross margin)

Provide a sample sheet with formulas; use pilot results to adjust ΔL and ΔCR.

90-Day Execution Checklist (what to do immediately)

- Save the baseline audit report (Phase 0).

- Approve positioning statement and product one-pagers.

- Create org accounts (OpenAI, Pinecone, Zapier, Notion, media monitoring trial).

- Build a prompt library in Notion with the three starter prompts above and 10 more.

- Identify 2 pilot clients and sign pilot briefs (use pilot pricing).

- Run 2 internal training sessions (LLM basics & prompt engineering).

- Launch pilot #1 and schedule weekly demo.

Final Deliverables:

At the end of this roadmap execution, LIS Digital will have:

- Agency Baseline PDF including skills matrix, client fit matrix, and top 5 AI quick-win use cases.

- 4 AI Product One-Pagers (scope, deliverables, sample timeline, price range, KPIs).

- Updated Terms & Conditions draft with AI usage, data policy, and IP clauses.

- Pilot Environment Setup: org accounts (OpenAI, Pinecone, Zapier, Notion, media monitoring tool) + shared prompt library + automated media digest.

- Training Completion Report with role-based training pathway and 3 internal demo artifacts.

- 2–3 External Client Pilot Reports with KPIs vs baseline and conversion proposals.

- Sales & Marketing Collateral: product PDFs, sales deck, outreach templates, LinkedIn sequence, and ROI calculator.

- AI Transformation Roadmap Document (this document) is a strategic guide for scaling.

Next Steps:

To implement the roadmap, LIS Digital should proceed as follows:

- Approve positioning statement & 4 product one-pagers (Phase 1, Week 2).

- Set up organizational accounts for OpenAI, Pinecone, Zapier/Make, Notion, and a media monitoring tool (Phase 2, Week 3–4).

- Develop initial prompt library in Notion with at least 15 starter prompts (Phase 2, Week 4).

- Identify & confirm 2–3 pilot clients from the prioritized client list (Phase 0 outcome) (Phase 2, Week 5).

- Conduct internal training sessions on LLM basics, prompt engineering, and workflow design (Phase 3, Week 6–10).

- Run Pilot #1 with selected client and collect KPIs (Phase 4, Week 11–16).

- Prepare pilot reports & conversion proposals to turn pilots into retainer contracts (Phase 4, Week 16).

- Update website & marketing assets with AI positioning, service one-pagers, and pilot case studies (Phase 5, Week 17–20).

- Launch go-to-market campaign (sales outreach, LinkedIn ads, PR) to scale client acquisition (Phase 5, Week 20–24).